## Sheet1
KA\PG | Initiation |  |  | Planning |  |  | Executing |  |  | Monitoring & Controlling |  |  | Closing
| Inputs |  | Outputs | Inputs |  | Outputs | Inputs |  | Outputs | Inputs |  | Outputs | Inputs |  | Outputs
Integration | SOW | [7 empty] | Deliverables
| Business Needs | Create Project Charter | Project Charter | Output from Planning Processes | Develop Project Mgt Plan | Project Mgt Plan | Approved Change Requests | Direct & Mge Project Exec. | Change Requests | Performance Reports | Monitor & Control Project work | Change Requests | Accepted deliverables | Close Project | Final Product, Service or Result Transition
| Contract |  |  | Project Charter | Expert Judgement |  |  | PMIS | Work Performance Info |  | Expert Judgement |  |  | Expert Judgment | OPA Updates
[10 empty] | Work Performance Info | Perform Integrated Change Control | Change Requests Status Update
[10 empty] | Change requests | Change Requests Meetings
Scope |  |  |  | Project Charter | Collect Requirement | Req Documentation |  |  |  | Req Documentation | Verify scope | Accepted Deliverables
|  |  |  | Stakeholer Register | [5 empty] | Validated Deliverables | Inspection | Change Requests
|  |  |  | Project Charter | Define Scope | Project Scope Statement |  |  |  | Req Documentation | Control scope | Work Performance measurements
|  |  |  | Req. Documentation | Product Analysis |  |  |  |  | Work Performance Info | Variance analysis | Change Requests
|  |  |  | Project Scope Statement |  | WBS
|  |  |  | Req Documentation | Create WBS | WBS Dictionary
[5 empty] | Decomposition | Scope Baseline
Time |  |  |  | Scope Baseline | Define Activities | Activity List
[5 empty] | Decomposition | Activity Attributes
[5 empty] | Rolling Wave Planning | Mile Stones
|  |  |  | Activity List | Sequence Activities | Project Schedule Netwoork Diagram
|  |  |  | Project Scope Statement | PDM
|  |  |  | Activity List | Estimate Activity Resources | Activity Resource req. |  |  |  | Work Performance Info | Control schedule | Work performance Measurements
|  |  |  | Activity attributes |  | RBS |  |  |  | Project Schedule | Variance analysis | Change Requests
|  |  |  | Resource Calendar | [6 empty] | Resource-leveling
|  |  |  | Activity Resource req. | Estimate Activity Duration | Activity Duration estimates
Resource Calendar
|  |  |  | Activity Duration Estimates | Develope Schedule | Project Schedule
Schedule Baseline
Cost |  |  |  | Scope Baseline
|  |  |  | Project schedule | Estimate Activity Cost | Activity Cost estimates |  |  |  | Project Funding Req. | Control cost | Budget Forecast
|  |  |  | Human Resource Plan | [5 empty] | Work Performance Info | Variance analysis | Change Requests
|  |  |  | Activity Cost Estimates | Determine Budget | Cost Performance Baseline
Project Funding Requirement
Quality | [5 empty] | Quality Checklist | Work performance info |  |  | Work Performance Measurements |  | Quality Control Measurements
|  |  |  | Scope, Schedule, Cost BL | Plan Quality | Quality Metrics | Quality Metrics | Perform Quality Assurance | Change Requests | Deliverables | Perform Quality Control | Validated deliverables
|  |  |  | Stakeholer & Risk Register | Benchmark | Process Improvement Plan | Quality Control Measure. | Quality Audits |  | Approved Change Requests | Cause & Effect Diagram | Change Requests
[5 empty] | DoE |  |  | Process Analysis |  |  | Control charts
HR | [6 empty] | HR Plan | Acquire Project Team | Resource Calendar |  | Flowcharting
|  |  |  | Activity Resource requrements | Develope HR Plan | HR Plan |  | Pre-assignment |  |  | Histogram
[7 empty] | Resource Calendar | Develop Project Team | Team Performance Assessment |  | Pareto chart
[8 empty] | Recognition & Rewards |  |  | Run Chart
[8 empty] | Ground Rules & Training |  |  | Scatter Diagram
[7 empty] | Project Staff Assignment | Manage Project Team |  |  | Statistical Sampling
[7 empty] | Performance reports | Project Performance Appraisal |  |  | Inspection
Conflict management
Communication | [9 empty] | Work Performance Measurements | Report Performance
| Project Charter | Identify Stakeholders | Stakeholder Register | Stakeholder Register | Plan Communication | Comm. Mgt. Plan | Performance reports | Ditribute Information | OPA updates | Work Performance Info | Variance analysis | Performance Reports
|  |  | Stakeholder Mgt. strategy | Stakeholder Mgt. Strategy |  |  |  | Communication Tool |  | Budget Forecast | Forecasting methods
[7 empty] | Stakeholder Register | Manage S.holder Expectations | Change Requests
[7 empty] | Issue Log | Communication Methods
Risk |  |  |  | Project scope statement | [5 empty] | Risk Register | Monitor & Control Risk
|  |  |  | Schedule & Cost Mgt. Plan | Plan Risk Managemnet | Risk Mgt. Plan |  |  |  | Work Performance Info | Risk Reassessment & Audit | Risk Register Updates
|  |  |  | Communication Mgt plan | [5 empty] | Performance Reports | Varisance & Trend Analysis | Change Requests
[5 empty] | Identify Risks | Risk Register |  |  |  |  | Reserve analysis
|  |  |  | Risk Register | Perform Qualitative Risk Anls | Risk Register Updates
|  |  |  | Risk Register | Perform Quantitative Risk Anls
|  |  |  | Risk Register | Plan Risk Response | Risk Register Updates
Risk Mgt. Plan
Procurement |  |  |  | Dcope Basaeline |  | Procurement Mgt. plan | Qualified Seller List | Conduct Procurement | Sellected sellers | Contract | Administer Procurement | Change Request | Proc. Documentation | Close Procurement | Closed Procurement
|  |  |  | Req. Documentation | Plan Procurement | Procurement Statement of Work | seller Proposals | Independent Estimates | Procurement Contract Award |  |  | Proc. Documentation |  | Negotiated Settlements
|  |  |  | Risk Register | Make-or-buy-Analysis | Make-or-buy-decision |  | Bidder Conference
[5 empty] | Contract Types |  |  | Proposal Evaluations Techniques