## Process Map
| Initiating | Planning | Executing | Monitor & Control | Closing
Integration | Develop Project Charter | Develop Proj. Mang. Plan | Direct & Manage Proj. Work | Monitor & Control Proj. Work | Close Project or Phase | INPUT
|  |  | Manage Project Knowledge | Perform Int. Change Control
Scope |  | Plan Scope Management |  | Validate Scope |  | TOOLS & TECH.
|  | Collect Requirements |  | Control Scope
|  | Define Scope |  |  |  | OUTPUT | Approved Change
Create WBS
Schedule |  | Plan Schedule Management |  | Control Schedule
Define Activities
Sequence Activities
Estimate Activity Durations
Develop Schedule
Cost |  | Plan Cost Management |  | Control Costs
Estimate Costs
Determine Budget
Quality |  | Plan Quality Management | Manage Quality | Control Quality
Resource |  | Plan Resource Management | Aquire Resources | Control Resources
|  | Estimate Resource Activities | Develop Team
Manage Team
Communications |  | Plan Communications Mangmt. | Manage Communications | Monitor Communications
Risk |  | Plan Risk Management | Implement Risk Responses | Monitor Risks
Identify Risks
Perform Qual. Risk Analysis
Perform Quan. Risk Analysis
Plan Risk Responses
Procurement |  | Plan Procurement Mangmt. | Conduct Procurements | Control Procurements
Stakeholder | Identify Stakeholders | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Monitor Stakeholder Engagement

## Process Info
ID | Knowledge Group | Project Management Process Group | Process | Input | Tools & Techniques | Outputs
4.1 | Project Integration Management | Initiating | Develop Project Charter | • Business Documents - Business Case • Agreements • EEFs • OPAs | • Expert judgement • Data Gathering - Brainstorming - Focus Groups - Interviews • Interpersonal & Team Skills - Conflict Management - Facilitation - Meeting Management • Meetings | • Project charter • Assumption log
4.2 | Project Integration Management | Planning | Develop Project Management Plan | • Project Charter • Outputs from "Plan" processes • EEFs • OPAs | • Expert judgement • Data Gathering - Brainstorming - Checklists - Focus Groups - Interviews • Interpersonal & Team Skills - Conflict Management - Facilitation - Meeting Management • Meetings | • Project management plan
4.3 | Project Integration Management | Executing | Direct and Manage Project Work | • Project management plan - ANY component • Project documents - Change log - Lessons learned register - Milestone list - Project communications - Project schedule - Requirements traceability matrix - Risk register - Risk report • APPROVED change requests • EEFs • OPAs | • Expert judgement • Project management information system (PMIS) • Meetings | • Deliverables • Work Performance Data • Issue log • Change Requests • Project management plan updates - Any component • Project documents updates - Activity list - Assumptions log - Lessons learned register - Requirements documentation - Risk register - Stakeholder register • OPAs updates
4.4 | Project Integration Management | Executing | Manage Project Knowledge | • Project management plan - ALL components • Project documents - Lessons learned register - Project team assignments - Resource breakdown structure - Stakeholder register • Deliverables • EEFs • OPAs | • Expert judgement • Knowledge management • Information management • Interpersonal and team skills - Active listening - Facilitation - Leadership - Networking - Political awareness | • Lesson learned register • Project management plan updates - Any component • OPAs updates
4.5 | Project Integration Management | Monitor & Control | Monitor & Control Project Work | • Project management plan - ANY component • Project documents - Assumption log - Basis of estimates - Cost forecasts - Issue log - Lessons learned register - Milestone list - Quality Reports - Risk register - Risk report - Schedule forecasts • Work performance information • Agreements • EEFs • OPAs | • Expert judgement • Data analysis - Alternative analysis - Cost-benefit analysis - Earned value analysis - Root cause analysis - Trend analysis - Variance analysis • Decision making - Voting • Meetings | • Work Performance reports • Change requests • Project management plan updates - ANY component • Project documents updates - Cost forecasts - Issue log - Lessons learned register - Risk register - Schedule forecasts
4.6 | Project Integration Management | Monitor & Control | Perform Integrated Chance Control | • Project management plan - Change management plan - Configuration management plan - Scope baseline - Schedule baseline - Cost baseline • Project documents - Basis of estimates - Requirements traceability matrix - Risk Report • Work performance reports • Change requests • EEFs • OPAs | • Expert judgement • Change control tools • Data analysis - Alternatives analysis - Cost-benefit analysis • Decision making - Voting - Autocratic decision making - Multicriteria decision analysis • Meetings | • Approved change requests • Project management plan updates - Any component • Project documents updates - Change log
4.7 | Project Integration Management | Closing | Close Project or Phase | • Project charter • Project management plan - ALL components • Project documents - ALL documents (-ish) • ACCEPTED deliverables • Business documents - Business case - Benefits management plan • Agreements • Procurement documentation • OPAs | • Expert judgement • Data analysis - Document analysis - Regression analysis - Trend Analysis - Variance Analysis • Meetings | • Project documents update - Lessons learned register • Final product, service, or result transition • Final report • OPAs updates
5.1 | Scope Management | Planning | Plan Scope Management | • Project Charter • Project management plan - Quality management plan - Project life cycle description - Development approach • EEFs • OPAs | • Expert judgement • Data analysis - Alternative analysis • Meetings | • Scope management plan • Requirements management plan
5.2 | Scope Management | Planning | Collect Requirements | • Project charter • Project management plan - Scope management plan - Requirements management plan - Stakeholder engagement plan • Project documents - Assumption log - Lessons learned register - Stakeholder register • Business documents - Business case • Agreements • EEFs • OPAs | • Expert judgement • Data gathering - Brainstorming - Interviews - Focus Groups - Questionnaires and surveys - Benchmarking • Data Analysis - Document analysis • Decision Making - Voting - Autocratic - Multicriteria • Data representation - Affinity diagrams - Mind mapping • Interpersonal and team skills - Nominal group technique - Observation/conversations - Facilitation • Context diagrams • Prototypes | • Requirements documentation • Requirements traceability matrix
5.3 | Scope Management | Planning | Define Scope | • Project charter • Project management plan - Scope management plan • Project documents - Assumption log - Requirements documentation - Risk register • EEFs • OPAs | • Expert judgement • Data analysis - Alternative analysis • Decision making - Multicriteria • Interpersonal and team skills - Facilitation • Product analysis | • Project scope statement • Project documents updates - Assumption log - Requirements documentation - Requirements traceability matrix - Stakeholder register
5.4 | Scope Management | Planning | Create WBS | • Project management plan - Scope management plan • Project documents - Project scope statement - Requirements documentation • EEFs • OPAs | • Expert judgement • Decomposition | • Scope baseline • Project documents updates - Assumption log - Requirements documentation
5.5 | Scope Management | Monitor & Control | Validate Scope | • Project management plan - Scope management plan - Requirements management plan - Scope baseline • Project documents - Lessons learned register - Quality reports - Requirements documentation - Requirements traceability matrix • Verified deliverables • Work performance data | • Inspection • Decision making - Voting | • Accepted deliverables • Work performance information • Change requests • Project document updates - Lessons learned register - Requirements documentation - Requirements traceability matrix
5.6 | Scope Management | Monitor & Control | Control Scope | • Project management plan - Scope management plan - Requirements management plan - Change management plan - Configuration management plan - Scope baseline - Performance measurement baseline • Project documents - Lessons learned register - Requirements documentation - requirements traceability matrix • Work performance data • OPAs | • Data analysis - Variance analysis - Trend analysis | • Work performance information • Change requests • Project management plan updates - Scope management plan - Scope baseline - Schedule baseline - Cost baseline - Performance measurement baseline • Project documents updates - Lessons learned register - Requirements documentation - requirements traceability matrix
6.1 | Schedule Management | Planning | Plan Schedule Management | • Project charter • Project management plan - Scope management plan - Development approach • EEFs • OPAs | • Expert judgement • Data analysis - Alternative analysis • Meetings | • Schedule management plan
6.2 | Schedule Management | Planning | Define Activities | • Project Management Plan - Schedule management plan - Scope Baseline • EEFs • OPAs | • Expert judgement • Decomposition • Rolling wave planning • Meetings | • Activity list • Activity attributes • Milestone list • Change requests • Project management plan updates - Schedule baseline - Cost baseline
6.3 | Schedule Management | Planning | Sequence Activities | • Project management plan - Schedule management plan - Scope Baseline • Project documents - Activity attributes - Activity list - Assumption log - Milestone list • EEFs • OPAs | • Precedence diagramming method • Dependency determination and integration • Leads and lags • Project management information system (PMIS) | • Project schedule network diagrams • Project documents updates - Activity attributes - Activity list - Assumption log - Milestone list
6.4 | Schedule Management | Planning | Estimate Activity Durations | • Project management plan - Schedule management plan - Scope management plan • Project documents - Activity attributes - Activity list - Assumption log - Lessons learned register - Milestone list - Project team assignments - Resource breakdown structure - Resource calendars - Resource requirements - Risk register • EEFs • OPAs | • Expert judgement • Analogous estimating • Parametric estimating • Three-point estimating • Bottom-up estimating • Data analysis - Alternative analysis - Reserve analysis • Decision making - Voting • Meetings | • Duration estimates • Basis of estimates • Project documents updates - Activity attributes - Assumption log - Lessons learned register
6.5 | Schedule Management | Planning | Develop Schedule | • Project management plan - Schedule management plan - Scope management plan • Project documents - Activity attributes - Activity list - Assumption log - Basis of estimates - Duration estimates - Lessons learned register - Milestone list - Project schedule network diagrams - Project team assignments - Resource calendars - Resource requirements - Risk register • Agreements • EEFs • OPAs | • Schedule network analysis • Critical path method • Resource optimization • Data analysis - What-if scenario analysis - Simulation • Leads and lags • Schedule compression • Project management information system (PMIS) • Agile release planning | • Schedule baseline • Project schedule • Schedule data • Project calendars • Change requests • Project management plan updates - Schedule management plan - Cost baseline • Project documents updates - Activity attributes - Assumption log - Duration estimates - Lessons learned register - Resource requirements - Risk register
6.6 | Schedule Management | Monitor & Control | Control Schedule | • Project management plan - Schedule management plan - Schedule baseline - Scope baseline - Performance measurement baseline • Project documents - Lessons learned register - Project calendars - Project schedule - Resource calendars - Schedule data • Work performance data • OPAs | • Data analysis - Earned value analysis - Iteration burndown chart - Performance reviews - Trend analysis - Variance analysis - What-if scenario analysis • Critical path method • Project management information system (PMIS) • Resource optimization • Leads and lags • Schedule compression | • Work performance information • Schedule forecasts • Change requests • Project management plan updates - Schedule management plan - Schedule baseline - Cost baseline - Performance measurement baseline • Project documents updates - Assumption log - Basis of estimates - Lessons learned register - Project schedule - Resource calendar - Risk register - Schedule data
7.1 | Cost Management | Planning | Plan Cost Management | • Project charter • Project management plan - Schedule management plan - Risk management plan • EEFs • OPAs | • Expert judgement • Data analysis - Alternative analysis • Meetings | • Cost management plan
7.2 | Cost Management | Planning | Estimate Costs | • Project management plan - Cost management plan - Quality management plan - Scope baseline • Project documents - Lessons learned register - Project schedule - Resource requirements - Risk register • EEFs • OPAs | • Expert judgement • Analogous estimating • Parametric estimating • Three-point estimating • Bottom-up estimating • Data analysis - Alternative analysis - Reserve analysis - Cost of quality • Project management information system (PMIS) • Decision making - Voting | • Cost estimates • Basis of estimates • Project documents updates - Assumption log - Lessons learned register - Risk register
7.3 | Cost Management | Planning | Determine Budget | • Project management plan - Cost management plan - Resource management plan - Scope baseline • Project documents - Basis of estimates - Cost estimates - Project schedule - Risk register • Agreements • EEFs • OPAs | • Expert judgement • Cost aggregation • Data analysis - Reserve analysis • Historical information review • Funding limit reconciliation • Financing | • Cost baseline • Project funding requirements • Project documents updates - Cost estimates - Project schedule - Risk register
7.4 | Cost Management | Monitor & Control | Control Costs | • Project management plan - Cost management plan - Cost baseline - Performance measurement baseline • Project documents - Lessons learned register • Project funding requirements • Work performance data • OPAs | • Expert judgement • Data analysis - Earned value analysis - Variance analysis - Trend analysis - Reserve analysis • To complete performance index • Performance management information system (PMIS) | • Work performance information • Cost forecasts • Change requests • Project management plan updates - Cost management plan - Cost baseline - Performance measurement baseline • Project documents updates - Assumption log - Basis of estimates - Cost estimates - Lessons learned register - Risk register
8.1 | Quality Management | Planning | Plan Quality Management | • Project charter • Project management plan - Requirements management plan - Risk management plan - Stakeholder engagement plan - Scope baseline • Project documents - Assumption log - Requirements documentation - Requirements traceability matrix - Risk register - Stakeholder register • EEFs • OPAs | • Expert judgement • Data gathering - Benchmarking - Brainstorming - Interviews • Data Analysis - Cost-benefit analysis - Cost of quality • Decision Making - Multicriteria decision analysis • Data representation - Flowcharts - Logical data model - Matrix diagrams - Mind mapping • Test and inspection planning • Meetings | • Quality management plan • Quality metrics • Project management plan updates - Risk management plan - Scope baseline • Project documents updates - Lessons learned register - Requirements traceability matrix - Risk register - Stakeholder register
8.2 | Quality Management | Executing | Manage Quality | • Project management plan - Quality management plan • Project documents - Lessons learned register - Quality control measurements - Quality metrics - Risk report • OPAs | • Data gathering - Checklists • Data analysis - Alternatives analysis - Document analysis - Process analysis - Root cause analysis • Decision making - Multicriteria decision analysis • Data representation - Affinity diagrams - Cause and effect diagrams - Flowcharts - Histograms - Matrix diagrams - Scatter diagrams • Audits • Design for X • Problem solving • Quality improvement methods | • Quality reports • Test and evaluation documents • Change requests • Project management plan updates - Quality management plan - Scope baseline - Schedule baseline - Cost baseline • Project documents updates - Issue log - Lessons learned register - Risk register
8.3 | Quality Management | Monitor & Control | Control Quality | • Project management plan - Quality management plan • Project documents - Lessons learned register - Quality metrics - Test and evaluation documents • Approved change requests • Deliverables • Work performance data • EEFs • OPAs | • Data gathering - Checklists - Check sheets - Statistical sampling - Questionnaires and surveys • Data analysis - Performance reviews - Root case analysis • Inspection • Testing/product evaluations • Data representation - Cause and effect diagrams - Control charts - Histogram - Scatter diagrams • Meetings | • Quality control measurements • Verified deliverables • Work performance information • Change requests • Project management plan updates - Quality management plan • Project documents updates - Issue log - Lessons learned register - Risk register - Test and evaluation documents
9.1 | Resource Management | Planning | Plan Resource Management | • Project charter • Project management plan - Quality management plan - Scope baseline • Project documents - Project schedule - Requirements documentation - Risk register - Stakeholder register • EEFs • OPAs | • Expert judgement • Data representation - Hierarchical assignment matrix - Text-oriented formats • Organizational theory • Meetings | • Resource management plan • Team charter • Project documents updates - Assumption log - Risk register
9.2 | Resource Management | Planning | Estimate Resource Activity | • Project management plan - Resource management plan - Scope baseline • Project documents - Activity attributes - Activity list - Assumption log - Cost estimates - Resource calendars - Risk register • EEFs • OPAs | • Expert judgement • Bottom-up estimating • Analogous estimating • Parametric estimating • Data analysis - Alternatives analysis • Project management information system (PMIS) • Meetings | • Resource requirements • Basis of estimates • Resource breakdown structure • Project documents updates - Activity attributes - Assumption log - Lessons learned register
9.3 | Resource Management | Executing | Acquire Resources | • Project management plan - Resource management plan - Cost baseline • Project documents - Project schedule - Resource calendars - Resource requirements -Stakeholder register • EEFs • OPAs | • Decision making - Multicriteria decision analysis • Interpersonal and team skills - Negotiation • Pre-assignment • Virtual teams | • Physical resource assignments • Project team assignments • Resource calendars • Change requests • Project management plan updates - Resource management plan - Cost baseline • Project documents updates - Lessons learned register - Project schedule - Resource breakdown structure - Resource requirements - Risk register - Stakeholder register • EEF updates • OPA updates
9.4 | Resource Management | Executing | Develop Team | • Project management plan - Resource management plan • Project documents - Lessons learned register - Project schedule - Project team assignments - Resource calendars - Team charter • EEFs • OPAs | • Colocation • Virtual Teams • Communication technology • Interpersonal and team skills - Conflict management - Influencing - Motivation - Negotiation - Team building • Recognition and rewards • Training • Individual and team assignments • Meetings | • Team performance assessments • Change requests • Project management plan updates - Resource management plan • Project documents updates - Lessons learned register - Project schedule - Project team assignments - Resource calendars - Team charter • EEF updates • OPA updates
9.5 | Resource Management | Executing | Manage Resources | • Project management plan - Resource management plan • Project documents - Issue log - Lessons learned register - Project team assignments - Team charter • Work performance reports • Team performance assessments • EEFs • OPAs | • Interpersonal and team skills - Conflict management - Decision making - Emotional intelligence - Influencing - Leadership • Project management information system (PMIS) | • Change requests • Project management plan updates - Resource management plan - Schedule baseline - Cost baseline • Project documents updates - Issue log - Lessons learned register - Project team assignments • EEF updates
9.6 | Resource Management | Monitor & Control | Control Resources | • Project management plan - Resource management plan • Project documents - Issue log - Lessons learned register - Physical resource assignments - Project schedule - Resource breakdown structure - Resource requirements - Risk register • Work performance data • Agreements • OPAs | • Data analysis - Alternatives analysis - Cost benefit analysis - Performance reviews - Trend analysis • Problem solving • Interpersonal and team skills - Negotiation - Influencing • Project management information system (PMIS) | • Work performance information • Change requests • Project management plan updates - Resource management plan - Schedule baseline - Cost baseline • Project documents updates - Assumption log - Issue log - Lessons learned register - Physical resource assignments - Resource breakdown structure - Risk register
10.1 | Communications Management | Planning | Plan Communications Management | • Project charter • Project management plan - Resource management plan - Stakeholder engagement plan • Project documents - Requirements documentation - Stakeholder register • EEFs • OPAs | • Expert judgement • Communications requirements analysis • Communication technology • Communication models • Communication methods • Interpersonal and team skills - Communication styles assessment - Political awareness - Cultural awareness • Data representation - Stakeholder engagement assessment matrix • Meetings | • Communication management plan • Project management plan updates - Stakeholder engagement plan • Project documents updates - Project schedule - Stakeholder register
10.2 | Communications Management | Executing | Manage Communications | • Project management plan - Resource management plan - Communications management plan • Project documents - Change log - Issue log - Lessons learned register - Quality report - Risk report - Stakeholder register • Work performance reports • EEFs • OPAs | • Communication technology • Communication methods • Communications skills - Communication competence - Feedback - Nonverbal - Presentations • Project management information system (PMIS) • Interpersonal and teams skills - Active listening - Conflict management - Cultural awareness - Meeting management - Networking - Political awareness • Meetings | • Project communications • Project management plan updates - Communication management plan - Stakeholder engagement plan • Project documents updates - Issue log - Lessons learned register - Project schedule - Risk register - Stakeholder register • OPA updates
10.3 | Communications Management | Monitor & Control | Monitor Communications | • Project management plan - Resource management plan - Communications management plan - Stakeholder engagement plan • Project documents - Issue log - Lessons learned register - Project communications • Work performance data • EEFs • OPAs | • Expert judgement • Project management information system (PMIS) • Data representation - Stakeholder engagement assessment matrix • Interpersonal and team skills - Observation/conversation • Meetings | • Work performance information • Change requests • Project management plan updates - Communications management plan - Stakeholder engagement plan • Project documents updates - Issue log - Lessons learned register - Stakeholder register
11.1 | Risk Management | Planning | Plan Risk Management | • Project charter • Project management plan - All components • Project documents - Stakeholder register • EEFs • OPAs | • Expert judgement • Data analysis - Stakeholder analysis • Meetings | • Risk management plan
11.2 | Risk Management | Planning | Identify Risks | • Project management plan - Requirements management plan - Schedule management plan - Cost management plan - Quality management plan - Resource management plan - Risk management plan - Scope baseline - Schedule baseline - Cost baseline • Project documents - Assumption log - Cost estimates - Duration estimates - Issue log - Lessons learned register - Requirements documentation - Stakeholder register • Agreements • Procurement documentation • EEFs • OPAs | • Expert judgement • Data gathering - Brainstorming - Checklists - Interviews • Data analysis - Root cause analysis - Assumption and constraint analysis - SWOT analysis - Document analysis • Interpersonal and team skills - Facilitation • Prompt lists • Meetings | • Risk register • Risk report • Project documents updates - Assumption log - Issue log - Lessons learned register
11.3 | Risk Management | Planning | Perform Qualitative Risk Assessment | • Project management plan - Risk management plan • Project documents - Assumption log - Risk register - Stakeholder register • EEFs • OPAs | • Expert judgement • Data gathering - Interviews • Data analysis - Risk data quality assessment - Risk probability and impact assessment - Assessment of other risk parameters • Interpersonal and team skills - Facilitation • Risk categorization • Data representation - Probability and impact matrix - Hierarchical charts • Meetings | • Project documents updates - Assumption log - Issue log - Risk register - Risk report
11.4 | Risk Management | Planning | Perform Quantitative Risk Assessment | • Project management plan - Risk management plan - Scope baseline - Schedule baseline • Project documents - Assumption log - Basis of estimates - Cost estimates - Cost forecasts - Duration estimates - Milestone list - Resource requirements - Risk register - Risk report - Stakeholder register • EEFs • OPAs | • Expert judgement • Data gathering - Interviews • Interpersonal and team skills - Facilitation • Representation of uncertainty • Data analysis - Simulation - Sensitivity analysis - Decision tree analysis - Influence diagrams | • Project documents updates - Risk report
11.5 | Risk Management | Planning | Plan Risk Responses | • Project management plan - Resource management plan - Risk management plan - Cost baseline • Project documents - Lessons learned register - Project schedule - Project team assignments - Resource calendars - Risk register - Stakeholder register • EEFs • OPAs | • Expert judgement • Data gathering - Interviews • Interpersonal and team skills - Facilitation • Strategies for threats • Strategies for opportunities • Contingent response strategies • Strategies for overall project risk • Data analysis - Alternative analysis - Cost-benefit analysis • Decision making - Multicriteria decision making | • Change requests • Project management plan updates - Schedule management plan - Cost management plan - Quality management plan - Resource management plan - Procurement management plan - Scope baseline - Schedule baseline - Cost baseline • Project documents updates - Assumption log - Cost forecasts - Lessons learned register - Project schedule - Project team assignments - Risk register - Risk report
11.6 | Risk Management | Executing | Implement Risk Responses | • Project management plan - Risk management plan • Project documents - Lessons learned register - Risk register - Risk report • OPAs | • Expert judgement • Interpersonal and team skills - Influencing • Project management information system (PMIS) | • Change requests • Project documents updates - Issue log - Lessons learned register - Project team assignments - Risk register - Risk report
11.7 | Risk Management | Monitor & Control | Control Risks | • Project management plan - Risk management plan • Project documents - Issue log - Lessons learned register - Risk register - Risk report • Work performance data • Work performance reports | • Data analysis - Technical performance analysis - Reserve analysis • Audits • Meetings | • Work performance information • Change requests • Project management plan updates - ANY component • Project documents updates - Assumption log - Issue log - Lessons learned register - Risk register - Risk report • OPA updates
12.1 | Procurement Management | Planning | Plan Procurement Management | • Project charter • Business documents - Business case - Benefits management plan • Project management plan - Scope management plan - Quality management plan - Resource management plan - Scope baseline • Project documents - Milestone list - Project team assignments - Requirements documentation - Requirements traceability matrix - Resource requirements - Risk register - Stakeholder register • EEFs • OPAs | • Expert judgement • Data gathering - Market research • Data analysis - Make or buy analysis • Source selection analysis • Meetings | • Procurement management plan • Procurement strategy • Bid documents • Procurement statement of work • Source selection criteria • Make or buy decisions • Independent cost estimates • Change requests • Project documents updates - Lessons learned register - Milestone list - Requirements documentation - Requirements traceability matrix - Risk register - Stakeholder register • OPA updates
12.2 | Procurement Management | Executing | Conduct Procurements | • Project management plan - Scope management plan - Requirements management plan - Communications management plan - Risk management plan - Procurement management plan - Configuration management plan - Cost baseline • Project documents - Lesson learned register - Project schedule - Requirement documentation - Risk register - Stakeholder register • Procurement documentation • Seller proposals • EEFs • OPAs | • Expert judgement • Advertising • Bidder conferences • Data analysis - Proposal evaluation • Interpersonal and team skills - Negotiation | • Selected sellers • Agreements • Change requests • Project management plan updates - Requirements management plan - Quality management plan - Communications management plan - Risk management plan - Procurement management plan - Scope baseline - Schedule baseline - Cost baseline • Project documents updates - Lessons learned register - Requirements traceability matrix - Requirements traceability matrix - Resource calendars - Risk register - Stakeholder register • OPA updates
12.3 | Procurement Management | Monitor & Control | Control Procurements | • Project management plan - Requirements management plan - Risk management plan - Procurement management plan - Change management plan - Schedule baseline • Project documents - Assumption log - Lessons learned register - Milestone list - Quality reports - Requirement documentation - Requirements traceability matrix - Risk register - Stakeholder register • Agreements • Procurement documentation • Approved change requests • Work performance data • EEFs • OPAs | • Expert judgement • Claims administration • Data analysis - Performance reviews - Earned value analysis - Trend analysis • Inspection • Audits | • Closed procurements • Work performance information • Procurement documentation updates • Change requests • Project management plan updates - Risk management plan - Procurement management plan - Schedule baseline - Cost baseline • Project documents updates - Lessons learned register - Resource requirements - Resource traceability matrix - Risk register - Stakeholder register • OPA updates
13.1 | Stakeholder Management | Initiating | Identify Stakeholders | • Project charter • Business documents - Business case - Benefits management plan • Project management plan - Communication management plan - Stakeholder engagement plan • Project documents - Change log - Issue log - Requirements documentation • Agreements • EEFs • OPAs | • Expert judgement • Data gathering - Questionnaire and surveys - Brainstorming • Data analysis - Stakeholder analysis - Document analysis • Data representation - Stakeholder mapping/representation • Meetings | • Stakeholder register • Change requests • Project management plan updates - Requirements management plan - Communication management plan - Risk management plan - Stakeholder engagement plan • Project documents updates - Assumption log - Issue log - Risk register
13.2 | Stakeholder Management | Planning | Plan Stakeholder Engagement | • Project charter • Project management plan - Resource management plan - Communications management plan - Risk management plan • Project documents - Assumption log - Change log - Project schedule - Risk register - Stakeholder register • Agreements • EEFs • OPAs | • Expert judgement • Data gathering - Benchmarking • Data analysis - Assumption and constraint analysis - Root cause analysis • Decision making - Prioritization/ranking • Data representation - Mind mapping - Stakeholder engagement assessment matrix • Meetings | • Stakeholder engagement plan
13.3 | Stakeholder Management | Executing | Manage Stakeholder Engagement | • Project management plan - Communications management plan - Risk management plan - Stakeholder engagement plan - Change management plan • Project documents - Change log - Issue log - Lessons learned register - Stakeholder register • EEFs • OPAs | • Expert judgement • Communications skills - Feedback • Interpersonal and team skills - Conflict management - Cultural awareness - Negotiation - Observation/conversation - Political awareness • Ground rules • Meetings | • Change requests • Project management plan updates - Communications management plan - Stakeholder engagement plan • Project documents updates - Change log - Issue log - Lessons learned register - Stakeholder register
13.4 | Stakeholder Management | Monitor & Control | Monitor Stakeholder Engagement | • Project management plan - Resource management plan - Communications management plan - Stakeholder engagement plan • Project documents - Issue log - Lessons learned register - Project communications - Risk register - Risk report • Work performance data • EEFs • OPAs | • Data analysis - Alternatives analysis - Root cause analysis - Stakeholder analysis • Decision making - Multicriteria decision analysis - Voting • Data representation - Stakeholder engagement assessment matrix • Communication skills - Feedback - Presentations • Interpersonal and team skills - Active listening - Cultural awareness - Leadership - Networking - Political awareness • Meetings | • Work performance information • Change requests • Project management plan updates - Resource management plan - Communications management plan - Stakeholder engagement plan • Project documents updates - Issue log - Lessons learned register - Risk register - Stakeholder register

## Data File
| Initiating | I | TT | O | Planning | I | TT | O | Executing | I | TT | O | Monitor & Control | I | TT | O | Closing | I | TT | O | IN | PL | EX | MC | CL
Integration | Develop Project Charter | 0 | 0 | 0 | Develop Proj. Mang. Plan | 0 | 0 | 0 | Direct & Manage Proj. Work | 0 | 0 | 0 | Monitor & Control Proj. Work | 0 | 0 | 0 | Close Project or Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INPUT | 0
[9 empty] | Manage Project Knowledge | 0 | 0 | 0 | Perform Int. Change Control | 0 | 0 | 1 | [6 empty] | 0 | 1
Scope |  |  |  |  | Plan Scope Management | 0 | 0 | 0 |  |  |  |  | Validate Scope | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  | TOOLS & TECH. | 0
[5 empty] | Collect Requirements | 0 | 0 | 0 |  |  |  |  | Control Scope | 0 | 0 | 0 | [5 empty] | 0 |  | 0
[5 empty] | Define Scope | 0 | 0 | 0 | [13 empty] | 0 |  |  |  | OUTPUT | Approved Change
[5 empty] | Create WBS | 0 | 0 | 0 | [13 empty] | 0
Schedule |  |  |  |  | Plan Schedule Management | 0 | 0 | 0 |  |  |  |  | Control Schedule | 0 | 0 | 0 | [5 empty] | 0 |  | 0
[5 empty] | Define Activities | 0 | 0 | 0 | [13 empty] | 0
[5 empty] | Sequence Activities | 0 | 0 | 0 | [13 empty] | 0
[5 empty] | Estimate Activity Durations | 0 | 0 | 0 | [13 empty] | 0
[5 empty] | Develop Schedule | 0 | 0 | 0 | [13 empty] | 0
Cost |  |  |  |  | Plan Cost Management | 0 | 0 | 0 |  |  |  |  | Control Costs | 0 | 0 | 0 | [5 empty] | 0 |  | 0
[5 empty] | Estimate Costs | 0 | 0 | 0 | [13 empty] | 0
[5 empty] | Determine Budget | 0 | 0 | 0 | [13 empty] | 0
Quality |  |  |  |  | Plan Quality Management | 0 | 0 | 0 | Manage Quality | 0 | 0 | 0 | Control Quality | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Resource |  |  |  |  | Plan Resource Management | 0 | 0 | 0 | Aquire Resources | 0 | 0 | 0 | Control Resources | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
[5 empty] | Estimate Resource Activities | 0 | 0 | 0 | Develop Team | 0 | 0 | 0 | [9 empty] | 0 | 0
[9 empty] | Manage Team | 0 | 0 | 0 | [10 empty] | 0
Communications |  |  |  |  | Plan Communications Mangmt. | 0 | 0 | 0 | Manage Communications | 0 | 0 | 0 | Monitor Communications | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Risk |  |  |  |  | Plan Risk Management | 0 | 0 | 0 | Implement Risk Responses | 0 | 0 | 0 | Monitor Risks | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
[5 empty] | Identify Risks | 0 | 0 | 0 | [13 empty] | 0
[5 empty] | Perform Qual. Risk Analysis | 0 | 0 | 0 | [13 empty] | 0
[5 empty] | Perform Quan. Risk Analysis | 0 | 0 | 0 | [13 empty] | 0
[5 empty] | Plan Risk Responses | 0 | 0 | 0 | [13 empty] | 0
Procurement |  |  |  |  | Plan Procurement Mangmt. | 0 | 0 | 0 | Conduct Procurements | 0 | 0 | 0 | Control Procurements | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Stakeholder | Identify Stakeholders | 0 | 0 | 0 | Plan Stakeholder Engagement | 0 | 0 | 0 | Manage Stakeholder Engagement | 0 | 0 | 0 | Monitor Stakeholder Engagement | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
[26 empty] | TOOLS & TECH. | 0
[26 empty] | OUTPUT | Approved Change