## 1_PIM
Develop Project Charter
allows PM to spend resources
developed by sponsor or PM in collaboration with initiating entity
Project charter 'DOES NOT' require Integrated (formal) change control to modify; Proj. charters are NOT normally changed, and even if it was, information is included as addendum;
NOTE: stake holder satisfaction is a key project objectve, and usually involves measurement criteria. Don't treat as intangible that’s 'not' a must have.
Note: projects are initiated by an entity external to project (eg. sponsor, program or PMO, or portfolio gov. body,), and these entitites have authority to terminate the project not the PM
I/P | T/T | O/P
Business Documents : Business Case | Expert Judgement | Project Charter - project purpose - measurable project obj. and success criteria - high level reqts. - high level proj. descrp., boundaries and key deliverables - overall project risk - summary milestone schedule - key stakeholder list - preapproved financial resources - proj. exit criteria - project approval reqts. (what constitues project success - who decides that and who signs off on project) - PM assigned and authority - Sponsor Name and Authority (or other approval entity for charter)
Agreements (eg. Contract if project is external) | Data Gathering: Brainstorm, focus grp, interview | Assumption Log
EEF | Interpers and Team Skills: Conflict Mgmt, Facilitation, Meeting Mgmt
OPA | Meetings
Develop Proj Mgmt Plan
All components of project mgmt plan, unless otherwise stated, require formal change control
I/P | T/T | O/P
Project Charter | Expert Judgement | Proj Mgmt Plan (includes all plans - eg. scope mgmt plan, qual mgmt plan; all baselines - scope schedule cost, proj life cycle, development approach (iterative, waterfall - predictive etc.) and additional components: change mgmt, config mgmt, mgmt reviews
O/P from other processes | Data Gathering: Brainstorm, focus grp, intervew + 'Checklist'! - just a forget me not list
EEF | Interpers and Team Skills: Conflict Mgmt, Facilitation, Meeting Mgmt
OPA | Meetings (project execution starts with kick off)
Note: Once baselined, proj. mgmt plan may only be changed thru 'Perform Intergrated Change Control'
Direct and Manage Proj Work (lead and direct work outlined in proj mgmt plan and implement approved changes)
I/P | T/T | O/P
Manage Project Knowledge
I/P | T/T | O/P
Monitor and Control Project Work (tracking, reviewing, reporting overall progress to meet perf. obj. defined in proj mgmt plan)
Monitoring: observing; Controlling: analyzing trends, variances and recommending actions
I/P | T/T | O/P
Proj Mgmt Plan (any component)
Project Documents (assumption log - validate, basis of estimates - validate, cost forecasts - is proj within defined tolerance range for budget?, milestone list, issue log - issue resolution status check, risk register, risk report - risk status check, quality reports - what defects and what freq, schedule forecasts etc.)
Work performance "INFORMATION" (= work perf. data collected and compared with proj mgmt plan components, proj docs, and see how proj is performing)
Agreements (eg. Procurement agreements - any deviations?, outsourced work - any shortcomings? etc.)
EEF
OPA
Perform Integrated Change Control
All components of project mgmt plan, unless otherwise stated, require formal change control
All project documents, unless otherwise stated, require formal change control
NOTE: decision of the CCB (change control board) is automatically documented in the change log
NOTE: note even an authorised individual can approve changes, e.g. project sponsor; In most cases these individuals will ask the PM to bear burden of conducting the analysis on the change and what impact it has
I/P | T/T | O/P
Proj Mgmt Plan (Change Mgmt Plan (which indiv. or group is resp. for reviewing and making decisions on change requests, eg. establishment of CCB), Config Mgmt Plan (procedures used to track project artifacts and monitor/control changes to those eg. Revision levels on dwgs), Scope Schedule Cost baselines)
Proj Docs (basis of estimates (impact of change requested on time, budget, resources), change log, reqt. traceability matrix (assess impact of change on proj scope), risk report (sources of proj risk involved by change requested))
Work performance reports (resource availablity, schedule and cost data, earned value reports, burnup/burn down charts)
Change Requests (corrective action, preventive action, defect repair, or updates) and impact on baselines
EEF
OPA
Close Project or Phase
Activities needed for adminstrative closure of a project: - actions and activities to satisfy completion of phase or project or to meet exit criteria (eg. conducting a phase review - similar to a gate review) - activities related to closure of contractual agreements - activities to collect proj. records, manage and archive project knowledge - activities to transfer project's products, services or results to next phase and/or to production/operations - collecting updates to OPA - measuring stakeholder satisfaction - investigate and documents reasons for 'actions taken upon' project termination before completion (note: reasons for project termination are not asked here)
I/P | T/T | O/P
| Expert Judgment | Proj Docs Updates (Lessons Learned Register)
| Data Analyses (Document, Regression, Trend, Variance - last 3 for improving perf. on future proj) | Final product/service/result transition
| Meetings | Final report (for project or phase) - summary descrip. of project or phase - how scope, quality, cost and schedule objectives were met - summary validation info. - how final prod./result/service achieved business needs outlined in the business plan and if not realized yet how they 'would' be realized - summary of risks encountered and how they were addressed
OPA Updates (eg. Operational support documents, project or phase closure documents - fomal documentation of completion or noting why the project was terminated and formalizes procedures for transfer of the finished and unfinished deliverables of the project to others)

## 2_PSPM
Plan scope mgmt
documents how product and project scope will be defined, validated and controlled
I/P | T/T | O/P
Project charter | Expert judgment | Scope mgmt plan (process for - creating project scope stat., - WBS creation from scope stat. (no limit on # of lvls.), - how scope baseline will be approved & maintained, - how completed deliverables are formally accepted)
Proj mgmt Plan (qual mgmt plan - bcos more DVP adds work, project lifecycle description, development approach) | Data analyses (alternatives - various ways of collecting reqts., defining scope etc. are analyzed) | Requirement Mgmt plan (how reqts. will be planned, tracked and prioritized along with metrics)
EEF | Meetings
OPA
Collect reqts.
I/P | T/T | O/P
Project charter | Expert Judgment | Reqts. Documentation ("Cornerstone of stakeholder acceptance")
Proj mgmt plan - scope mgmt plan - reqt mgmt plan - stakeholder engagement plan | Data gathering (brainstorming, interviews, focus grp, questionaire&survey - useful for large # of respondents, benchmarking) | Reqt. Traceability matrix (RTM) - link from product reqt. to deliverables that satisfy them
Proj docs - Assumptions log - lessons learned register - stakeholder register | Data analyses (document analyses) - eg. RFP review
Business Docs - buss case | Decision making (voting, autocratic decision making, multicriteria decision analyses)
Agreements | Data rep. : affinity diagr. - large # of ideas classified into grps. for analyses; mind mapping - consolidates indvl. brainstorms and shows simil. and diff. in ideas and is a diagram that spawns from a point and records each idea as a branch of its parent idea, helpful for keeing trail
EEF | Interpers. and team skill (nominal group tech. - ranking of brainstormed ideas by voting, obs/conv., facilitation - eg. QFD, user stories - descriptions of required functionality phrased as a short sentence)
OPA | Context diagr. (visual descrip. of product Scope)
Prototypes
Define scope
detailed descrip. of project and product from the reqts. documentation (iterative process, done at various points on the project)
NOTE: Added functionality (addtional Scope) by a member of project team rquires approval through 'Intergrated Change Control', because of adverse effects (eg. risks, incompatibility with system) that functionality may have even if it was done at no additional cost or time to project; As PM reject any additional functionality and if already made, ask team member to remove (In some cases, it may be possible to inform customer that this has been added and do nothing till decision of change control comes through)
I/P | T/T | O/P
Project charter | Expert judgment | Proj. scope statement (progr. elaborated scope descrip. + deliverables + acceptance criteria for deliverables + proj. exclusions - what's not in proj. scope)
Proj. mgmt plan (scope mgmt plan) | Data analyses (alternatives analysis) | Proj. document updates - assumption log - reqts. documentation - RTM - stakeholder register
Proj Documents - Assumption Log - Requirements Documentation - Risk Register | Decision Making (multi criteria decision analysis)
EEF | Interpersonal and team skills (facilitation)
OPA | Product Analysis (asks questions abt a product/service and forms answers that describe the use, characterisitics; examples include: product breakdown, requirements analysis, systems analysis, systems engg., VA/VE)
Create WBS
Hierarchical decomposition of total scope of work to be carried out by team to accomplish proj. objectives and create reqd. deliverables
Planned work is contained within the lowest level of the WBS components, which are called work packages
Limit one deliverable to one work package
No limit on # of levels of decomposition, but there is such as thing as too much leading to non productiveness; PM has authority to decide how far to decompose;
I/P | T/T | O/P
Validate Scope
Formalizing acceptance of completed project deliverables (Verification: compliance with a reqt. or spec.; Validation: meeting customer need)
Control Quality (Verification) vs. Validate Scope (Validation); Control Quality precedes Validate Scope;
I/P | T/T | O/P
Control Scope
Monitoring status of the project & product scope and making changes to the scope baseline
I/P | T/T | O/P
Work performance information
Change Requests
Proj. mgmt. plan updates - scope mgmt. plan - scope baseline - schedule baseline - cost baseline - performance measurement baseline
Proj docs. updates - lessons learned register - reqts. documentation - RTM

## 3_PSHM
Plan schedule mgmt
defines procecure/policy for planning, developing, controlling project schedule
I/P | T/T | O/P
Project charter | Expert judgment | Schedule mgmt plan: (this is the HOW!) - proj. schedule model development: scheduling method + schedule tool used (predictive: gantt/milestone; adaptive: kanban board/velocity/burndown chart of user stories) - Release and iteration length - in adaptive, the time boxed periods specified for releases, waves and iterations - Level of accuracy - acceptable range of activity duration estimates; Eg. If duration = 2 days +/-0.5 day, then level of accuracy is 0.5 day (side note: precision is round up/down of estm.) - Units of measure - organizational Procedural links (links WBS control accounts to performing organisation) - proj schedule model maintenance - how tracking is done on the schedule - Control thresholds - variations in schedule (duaration , start/finish) above which action is needed. Typically % dev. - Rules of perf. meas: how to call % complete, EVM techniques., Schedule perf. measurements (SV, SPI) - Reporting format and frequency
Proj mgmt plan: - Scope mgmt plan - Development approach | Data analyses (alternatives analyses - which scheduling method - network diagramming, EVM etc., to use or better to combine methods etc.)
EEF | Meetings
OPA
Define activities
defines activities (not the deliverables) under each work package (conducted throughout proj. per prog elaboration/rolling wave planning)
Activities: specfic actions to be performed to produce deliverables
I/P | T/T | O/P
Sequence activities
I/P | T/T | O/P
Proj mgmt plan - schedule mgmt plan - scope baseline | Precedence diagramming method (technq. to construct a schedule model where activities rep. as nodes and graphically linked to show sequence; SS, FF, SF,FS relationships) | Project schedule network diagrams/node diagr. (graphical o/p of the logical relationships b/w activities with pred. and succ.) The schedule network diagram is a schedule model.
Project docs - activity attributes - activity list - assumption log - milestone list | Dependency determination and integration (types of dependancy: mand., discr, int., ext.) | Project docs update: - activity attributes (eg. additional wait time) - activity list (add activities while sequencing) - assumption log - milestone list (dependencies could change milestones)
EEF | Leads and Lags (note this is separate from duration estms.)
OPA | PMIS (eg. Scheduling tool such as MS proj, Primavera, Jira)
Estimate activity durations
I/P | T/T | O/P
Proj mgmt plan - schedule mgmt plan - scope baseline | Expert judgment | Duration estimates
Project docs - activity attributes - activity list - assumption log - lessons learned register - milestone list - project team assignments & physical resource assignments (o/p of PRM: 'acquire resources') - resource breakdown structure (hierarchical structure of identified resource by type/catg. - resource calendars - resource requirements (o/p of 'PRM: Estimate activity resources') - risk register | Analogous estimating (aka top down estm.) | Basis of estimates
EEF | Paramatric estimating (uses stat. relationship b/w historical data and other variables/proj. para) - Parameters incl.: cubic m, sq ft., weight, # of materials, # of workers etc. | Proj docs updates: - activity attributes (activity duration estimates made part of this document) - assumption log (assumptions on resource skill and availablity + basis of estimates go into this log) - lessons learned register (efficienct techniques used in this process are documented, i.e. what worked well)
OPA | 3-point estimating (avg. of 3 time estimates): Simple mean/avg.: tE: (tO + tM + tP) / 3 Beta dist./Weighted average : tE: (tO + 4tM + tP) / 6 Std Dev = (tP - tO) / 6 +/- Range = tE +/- std dev.
Bottom-up estimating (aggregating estm. of lower level components of WBS) - time consuming but highly accurate
Data analyses (alternatives, reserve - determining amt .of contigency and mgmt reserve needed, i.e., amt. of schedule reserves)
Decision Making: voting, delphi (anonymous poll + process data)
Meeting
Develop schedule
I/P | T/T | O/P
Proj mgmt plan - schedule mgmt plan - scope baseline | Schedule network analysis (technique used to generate the proj. schedule model - eg. assess if schedule reserves are needed for crit. path tasks) | Schedule baseline (approved version of schedule model)
Project docs - activity attributes - activity list - assumption log - basis of estimates - duration estimates - lessons learned register - milestone list - proj schedule network diagrams - project team assignments - resource calendars - resource requirements (o/p of 'PRM: Estimate activity resources') - risk register | Critical path method (CPM) - Duration based on 3 pt. estm. and provides 80% chance of meeting deadline | Project schedule (ok to have resources unassigned)
Agreements | Resource Optimization Resouce levelling - delaying tasks when resource becomes available, may affect critical path; Resource smoothing - delaying task within their available free or total float; doesn't affect critical path | Project calendars (identifies working days and shifts available for scheduled activities)
EEF | Data analysis what-if scenario analyses - experiment scenarios on the network diagram; simulation - eg. Montecarlo analysis returning probab. on expected finish dates given repr. of uncertainty) | Change Request (mods. to schedule may change scope baseline)
OPA | Leads and Lags | Proj. mgmt plan updates: - schedule mgmt plan - cost baseline
| Schedule compression: crashing - reduce time by adding resources and increasing cost; fast tracking - parallel pathing activites where possible but carries risk of task rework/re-do/repeat; CCM (Critical chain method) - a reserve analyses method to prevent schedule slippage: Feeding buffer - usually added on non critical chain, 50% of feeding chain's duration to determine feeding buffer length, and placed after last task; task deadlines on the chain would then be set to latest start date and made to fill up the other 50% of time, resulting in zero available float. Project buffer - usually added on the critical chain, 50% of critical path's/ chain's duration to determine project buffer length, and placed after last task; task deadlines on the chain would then be set to latest start date and made to fill up the other 50% of time, resulting in zero available float. | Proj Docs update: - activity attributes - assumption log - duration estimates - lessons learned register - resource requirements (from WBS dictn.) - risk register
PMIS (eg. Scheduling software)
Agile release planning
Control schedule
Monitoring status of project to update proj. schedule and managing changes to schedule baseline
I/P | T/T | O/P
Proj mgmt Plan - schedule mgmt plan - schedule baseline - scope baseline - performance measurement baseline | Data analysis - Earned value analyses - Iteration burndown chart - expressed as actual remaining work vs. ideal remaining work; - a new finish date for the iteration is determined by forecast {using trend line} from the actual remaining work; - Velocity: avaerage work (eg. story points) per unit time (day); Possible to calculate both ideal velocity and actual velocity - Performance reviews (eg. how much work is done?)* - Trend analysis - Variance analysis - What-if scenario analyses *Measure Progress: 3 classes of effort: 1. discrete: measurable o/p 2. apportioned: % for tasks supporting discrete effort (eg. inspection or testing) 3. Letter of effort: no measurable objectives, but they do consume resources, hence can assign PV and EV! 4 methods for discrete effort: Fixed Formula = % Start:% Finish (eg. 25:75 = When starting fix 25% as done, only upon finishing can call 100% done) Weighted Milestone: assign % to deliverable, no partial credit on WIP Percent Complete: rate of using resources Physical measure: countable paremeters: length, qty. etc. | Work performance information (eg. SV, SPI)
Proj docs - lessons learned register - proj. calendars (any sudden vacation?) - proj. schedule - most important (eg. In formats such as gantt, network diag. or kanban board) - resource calendars - schedule data (activities, attributes, milestones, relationship, dependencies, schedule reserves etc.) | Critical path method | Schedule forecasts (predict conditions and future events, eg. Forecast trend line based on actual remaining work on the burndown chart)
Work performance data (i.e. the actuals) | PMIS | Change requests (rememeber no change to approved baseline without 'perform integrated change control' process)
OPA | Resource optimization | Proj. mgmt plan updates - Schedule mgmt plan - schedule baseline - cost baseline - perf. measurement baseline
| Leads and Lags | Proj docs updates - Assumption Log - Basis of estimates - Lessons learned register - Project schedule - Resource calendars - Risk register - Schedule data
Schedule Compression
Note: Assuming work starts on Day 1:
Duration = EF-ES +1 (or LF-LS+1)
But total float = LF-SF (or LS-ES)

## 4_PCSM
Plan cost mgmt
defines 'how' project cost will be estimated, budgeted, managed & controlled
I/P | T/T | O/P
Proj. charter | Expert judgment | Cost mgmt plan - units of measure - level of precision - level of accuracy - organizational procedural links - control thresholds - rules of performance measurement (e.g. which WBS points are needed to measure, EVM techq. - credits EV only upon 100% completion, tracking methods) - reporting format & freq. - others (descrip. of fund choice etc.)
Proj. mgmt plan - schedule mgmt plan - risk mgmt plan | Data analysis (alternative analysis - funding thru self: cash or equity or debt or how to acquire proj. resources: make/buy/lease/rent)
EEF | Meetings
OPA
Estimate costs
approximation of cost resources needed to complete project work
I/P | T/T | O/P
Proj. mgmt plan - cost mgmt plan - quality mgmt plan - scope baseline | Expert judgment | Cost estimates (direct: charged directly to project; indirect: across multiple proj., eg. Overheads; fixed : unchanged eg. Initial purchase cost for a machine; variable: depending on amt produced, eg. Material cost/unit; sunk: already incurred; opportunity cost: cost of giving up one option to gain another) Estimates can range from high level (ROM) to definitive estimates Note: sunk costs from one project, cannot be used as investment cost for a new project, even if that sunk cost in the old project delivers value for the new project; each project has to be viewed independently.
Proj. docs - lessons learned register - proj schedule - resource reqt. (labor, equipment, tool, office space, material etc.) - o/p of 'PRM: Estimate activity resources' - risk register (to help establish contingency) | Analogous Estimating | Basis of estimates (eg. Ranges, currency and even level of confidence)
EEF (labor rates: market conditions, currency exchange, inflation etc.) | Parametric Estimating | Proj. document updates: - assumption log - lessons learned register - risk register
OPA | Bottom up-estimating
Three-point analyses
Data analyses (alternatives analyses, reserve analyses, cost of quality)
PMIS
Decision making: voting
Determine budget (budgets are time based - i.e., when funding is needed?)
approximation of cost resources needed to complete project work
I/P | T/T | O/P
Control costs
monitoring status of proj. to updates costs and manage changes to cost baseline
I/P | T/T | O/P
Proj. mgmt plan - cost mgmt plan - cost baseline (If EVM, cost baseline = perf. meas. baseline) - performance measurement baseline | Expert judgement | Work performance information (eg. Result of earned value calculations)
Proj docs - lessons learned register | Data analyses (earned value, variance, trend reserve) Trend analyses:- EAC - estimate at completion given current performance, VAC (=BAC-EAC) <- variance at completion | Cost forecasts (calculated EAC or bottom up EAC is communicated to stakeholders) 4 methods: 1.) EAC = AC + New bottom up ETC (most accurate and time consuming) 2.) Cost Issue or Schedule Issues would not persist, i.e., project continues at expected rate EAC = AC + (BAC-EV) 3.) Cost Issues persist, EAC = BAC/CPI 4.) Cost and Schedule issues persist, EAC = AC + {(BAC-EV)/(SPI*CPI)}
Proj. funding requirements (how much and when you need to fund?) | To-complete performance index aka efficiency (Do I have enough money?) TCPI = (BAC-EV) / (BAC-AC); cost to finish divided by money remaining; Where overbudget, only in denominator, BAC can be replaced by EAC to validate the trend forecast; NOTE: BAC cannot be replaced by EAC in numerator because the numerator component is the amount of planned work remaining, rememeber even following a cost overrun (i.e. BAC - EAC < 0) the planned work aka scope of work has not changed! | Change requests (eg. Cost baselines changes due to say scope change, or change to cost estimates, activity resources availability changes etc.)
Work performance data (eg. Vendor invoices, material usage, other charge backs..) | PMIS | Proj. mgmt plan updates: - cost mgmt plan - cost baseline - performance measurement baseline
OPA (eg. Cost control tools, monitoring and reporting methods) |  | Proj docs. Update - assumption log - basis of estimates - cost estimates - lessons learned register - risk register

## 5_PQM
Plan quality mgmt
identifying quality reqts. and standards for the project (note that DVP is not being created here) and documenting how proj will show compliance to the qual. reqts.
Note Sigma Quality Levels: 1 Sig: 68.27%, 2 Sig: 95.45%, 3 Sig: 99.73%, 6 Sig: 99.99%(=3.4 dpmo) (note difference from sigma values)
I/P | T/T | O/P
Proj charter | Expert judgment | Quality mgmt plan - quality standards used by proj - quality obj. - quality roles & resp. - proj. deliverables and processes that need quality review - quality control and quality mgmt activities planned for proj - quality tools used for the project - quality procedures for the proj. (how to deal with non conformance, how to implement corrective action etc.)
Proj mgmt plan - reqts. mgmt plan - risk mgmt plan - stakeholder engn. plan - scope baseline | Data gathering - benchmarking - brainstorming - interviews | Quality metrics (proj or product attribute & how quality control process will verify compliance to it) - eg. % of task completed on time, CPI (for cost), failure rate, total down time per month, # of errors per line of code etc.
Proj docs - assumption log - reqts. documentation - RTM - risk register - stakeholder register | Data analyses - cost-benefit analyses - cost of quality | Proj mgmt plan updates - risk mgmt plan - scope baseline
EEF | Decision making - Multi criteria decision analysis (eg. Prioritization matrix - using a scorecard) | Proj documents updates - lessons learned register (challenges in coming up with qual mgmt plan) - reqt. traceability matrix - risk register - stakeholder register
OPA | Data representation - flowcharts - SIPOC {"supplier-input-process-output-customer" value chain} (examples of value chain showing how a complex process adds value to customers) - used for process improvement - logical data model - matrix diagrams - mind mapping
Test and inspection planning (detailed DVP not created here but overall plan is created!!)
Meetings
Manage quality (note that this process is still creating the validation plan, not running the DVP activities; however quality reports are created at the end usin the inspection/measurement data from control quality)
process of translating quality mgmt plan into executable quality activities that incorporate organisation's quality policies into project.
analysing whether project processes (not the work perf. data) are conforming to quality standards and identify areas of process improvements;
I/P | T/T | O/P
Control quality (this process involves the actual running the DVP, and measurements, i.e., verification activities)
monitoring and recording results of executing quality mgmt activities to assess performance and ensure proj. o/p are complete, correct
this process involves comparing work results (i.e. work perf. data) against the quality stds. set in the qual mgmt plan .
I/P | T/T | O/P
| Data gathering - checklists (to confirm compliance) - check sheets (aka tally sheets) - form of attribute sampling: yes/no - statistical sampling - form of variable sampling: continuous - questionnaries and surveys | Quality control measurements (results of measurement activities)
| Data analyses - performance reviews (compare plan to actual) - root cause analysis | Verified deliverables (I/P to 'Validate scope' for formal acceptance)
| Inspection (visual and involving gages/measurements) | Work performance information (eg. causes for rejection, reqts. already fulfilled, rework required etc.)
| Testing/product evaluations | Change requests
| Data representation - cause & effect diagrams (fishbone aka why-why aka ishikawa) - control charts (Note control limits are set by some stat. calc. and are tighter than specification limits - outside control limits means corrective action should be taken, points skewed towards one side of the mean, i.e., rule of 7, also are considered out of control) - histograms - scatter diagrams | Proj. mgmt plan updates (quality mgmt plan)
| Meetings - Approved change requests review - retrospectives/lessons learned | Proj. documents update - Issue log - Lessons learned register - Risk register - Test and evaluation documents (these are reviewed to make future tests more effective)

## 6_PRM
Resource Mgmt Methods (support lean)
Kaizen: continuous improvement
Just-in-time: right place at just the right time; reduced effect of poor quality
Total productive maintenance: goal to keep equipment at peak running condition
Theory of constraints: strives to reduce bottlenecks; idea to find the slowest manufacturing step, and requesting that no more material be sent than can be processed by that one step; then that step is investigated to be sped up until the next bottleneck somewhere else is revealed.
Theory of Motivation (Maslow's Hierarchy):
Physiological needs (food, clothing, meet basic body needs) -> Safety & security (incl. shelter & health for indiv. and loved ones) -> Love & belonging -> Self Esteem (become proud of own achievements and earn respect of others) -> Self Actualization (be the best you can be!)
Expectancy theory:
behaviour results from conscious choices; motivated by outcome; 3 factors: 1) expectancy (employee determines effort needed) 2.) instrumentality (employee determines if superior perf. leads to the outcome) 3.) valance (how much person wants reward or hates punishment)
Herzberg's motivators/ 2 factor theory
Dissatisfaction or hygiene (their absence causes the discontent) - e.g. company policy, salary, job security;
Satisfactional or motivational -eg. Achievement, recognition, respb., advancement and work itself;
Daniel Pink: "Truth abt what motivates us" - autonomy, mastery and purpose
Theory of Motivation (X,Y - Douglas McGregor; Z - from Japan):
X: labor intensive - manual, assy lines - non cognitive - employees viewed as lazy and needing supervision, and avoid resp. and lack ambition; authorative and punitive mgmt style
Y: employees are ambitious, self motivated; congntive jobs, and employees enjoy the mental challenges of their work, need space/freedom; facilitative mgmt style
Z: increases employee loyalty via job for life; mgmt. takes care of employee 'on' and 'off' the job; promote stable employment, high productivity, employee morale and satisfaction
Halo effect: assessment of one quality influences perception of some other quality (eg. Good looks means great abilty or good morals); demotivates others who may see the subject for who he/she really is
Plan resource mgmt
defining how to estimate, acquire, manage and use team & physical resources
I/P | T/T | O/P
Proj. charter (key stakeholder list, summary milestones, preapproved financial resources) | Expert judgment | Resource mgmt plan (team management plan + physical resource management plan) (be careful, no timetable comes out from this; this is only the 'how') - methods for identifying resources - guidance on how to acquire resources - what are the roles, responsibilities, skills/competencies, authorities needed? (eg. Purchase order signing authority) - proj. organisation charts - proj. team resource mgmt (guidance) - training - team development - physical resource control (info. on managing inventory, equipment & supplies) - recognition plan
Proj mgmt plan - quality mgmt plan (level of resources needed to maintain desired quality level) - scope baseline | Data representation - hierarchical charts - responsibilty assessment matrix {RAM} (shows proj. resource assigned to each work package) - eg. Activity on Y axis and Resource name on X axis and cells filled with R: responsbile, A: accountable (only 1 per activity), C: consult, I: information (folks on the fyi list) - text-oriented formats | Team charter (clear expectation regarding acceptable behaviours by team members) - team values - communication guidelines - decision making criteria and process - conflict resolution process
Proj docs - proj. schedule - reqts. documentation - risk register - stakeholder register | Organizational theory | Proj docs updates - assumption log - risk register
EEF (eg. Exisiting resources competencies and availability) | Meetings
OPA
Estimate activity resources
estimating team resources and the types and quantities of materials, equipments and supplies
I/P | T/T | O/P
Proj mgmt plan - resource mgmt plan - scope baseline - schedule baseline (not mentioned in pmBOK - but needed per Prepcast)
Proj docs - activity attributes (eg. 'Start/finish no earlier than date' constraints, pred., succ., lags, leads etc. - activity list - assumption log - cost estimates - resource calendars - risk register
EEF
OPA (eg. Published estimating data - how long does it take an excavator to dig a hole?)
Acquire resources
acquiring team members, facilities, equipment & supplies
this includes acquiring of independent contractors
End goal of this process: resources (both physical and human) are assigned
I/P | T/T | O/P
Proj. mgmt plan - resource mgmt plan - procurement mgmt plan (for infor. on resources from outside the project) - cost baseline
Proj docs - proj. schedule - resource calendars - resource reqts. - stakeholder register
EEF
OPA
Develop team
process of improving competencies, team member interaction and enhance team environ.
Tuckman's ladder: 5 stages of development for teams: Forming->Storming->norming->Performing->adjourning
I/P | T/T | O/P
Proj mgmt plan - resource mgmt plan | Colocation | Team performance "assessments" (not individual!) - these are indicators of the "team" strengths, weaknesses etc.
Proj. docs. - lessons learned register - proj. schedule - proj. team assignments - resource calendars - team charter | Virtual teams | Change requests (eg. Team building or training activities may affect cost)
EEF (eg. Human resource mgmt policies) | Communication technology | Proj. mgmt plan updates
OPA | Interpers. and team skills (aka soft skills) - conflict mgmt - influencing - motivation - negotiation - team building (activities that enhance social interaction - donuts, go-karting!) | Proj. docs. Updates - lessons learned register - proj. schedule (eg. add training/team building activities to schedule) - proj. team 'assignments' - resource calendars (update training 'out of office') - team charter
Recognition and Rewards (eg. Increase team involvement by soliciting team members' opinions)
Training
Individual and team "assessments"
Meetings
Manage team
process of tracking team member performance, providing feeback, resolving issues and managing team changes;
I/P | T/T | O/P
Proj. mgmt plan - resource mgmt plan | Interpersonal & team skills - conflict mgmt *collaborate (most positive, leading to win-win situation) *smooth/accommodate *compromise (seen as negative, i.e., an appeasement to both parties without solving the problem at hand & leading to lose-lose situation) *force *withdraw - decision making - emotional intelligence - influencing - leadership | Change requests (eg. staffing changes causing budget changes)
Proj. docs - issue log - lessons learned register - project team 'assignments' - team charter (typical in agile environments) | PMIS | Proj. mgmt plan updates - resource mgmt plan - schedule baseline - cost baseline
Work performance reports (o/p of 'PIM: Monitor and Control Project Work') - physical or electronic representation of the work performance info. where the comparison is done and inference can be drawn - eg. Tasks can be grouped by person and % completion by date can be tracked vs. estimate |  | Proj. docs updates - Issue log - Lessons learned register - project team 'assignments' (following any changes to assingments) - frequent not usually needing change request
Team performance "assessments" (continuous&regular) - o/p of PRM: 'Develop Team' |  | EEF updates - i/p to organizational performance appraisal (eg. i/p to employee TMS review by functional mgr) - personnel skill (what did a person start doing differently through this project, what skill did he/she gain?)
EEF (hoilday policy, PTO etc.)
OPA (eg. Turbocharge cards, team wear or customer swag/apparel)
Control resources
ensuring "physical" resources assigned to the proj. are available as planned and in the right quantity
& monitoring planned vs. actual utilization of resources and taking corrective action as necessary
I/P | T/T | O/P
Proj. mgmt plan - resource mgmt plan | Data analysis - alternatives analysis (eg. paying additional over time vs. late delivery) - cost-benefit analysis - performance reviews (planned vs. actual resource utilization) - trend analysis | Work performance information (drawing up a comparison b/w planned vs. actual)
Proj docs - issue log (eg. Delay in supplies, incorrect tools) - lessons learned register - physical resource assignments - project schedule - resource breakdown structure - resource requirements - risk register | Problem solving | Change requests
Work performance data (eg. Number and type of resources used already on project) - o/p of PIM: 'Direct and Manage Project work' | Interpersonal and team skills - negotiation - influencing | Proj. mgmt plan updates - resource mgmt. plan - schedule baseline* - cost baseline* * note that change to resource assignments would cause schedule, cost to vary but not scope
Agreements | PMIS | Proj docs. updates - assumption log - issue log - lessons learned register - physical resource assignments - resource breakdown structure - risk register
OPA

## 7_PCM
Plan communications management
how to develop appropriate plan/approach to project communications based on infor needs of stakeholders or other group and available OPA
categ. of comm.: external, internal, formal, informal
I/P | T/T | O/P
Project charter (list of key stakeholders possibly with roles and resp.) | Expert judgment | Communication mgmt plan - stakeholder communication reqts. - information to be communicated - escalation process - reason for distribution - timeframe for distribution and receipt of acknowledgment - persons who will be receiving the info. and person who will be sending the info - which documents to trash, which to save - constraints from legisation, regulation, technology limitations and org. policies etc.
Proj mgmt plan - resource mgmt plan (who are the resources needing to commnicate with) - stakeholder engagement plan | Communication reqt. analysis (determines info. needs of proj. stakeholders - i.e. type and format; eg. Choosing video conferencing format for weekly meetings) Uses - stakeholder information reqts. - # of comm. channels - org charts, proj. org. - proj. development approach (eg. Pred., adap.) etc. | Pro. Mgmt plan updates - stakeholder engagement plan
Proj docs - requirements documentation - o/p of PSPM: 'Collect reqts.' - stakeholder register | Communication technology | Proj. docs. Updates - proj. schedule (updated to include communication activities) - stakeholder register
EEF (eg. Local language needs) | Communication models: - sender/receiver (encode->transmit->decode; no feedback) - interactive (recipient acknowledges receipt and 'could' send feedback on what they took away from the message)
OPA | Communication methods (3 catg. of methods: push, pull, interactive) NOTE: video livecast of a construction progress thru a website is a 'pull' communication, because people have to login to website to access the info.
Interp. and team skills - communication styles assessment (identify preferred communication method, format & content for planned comm. activities) - often used with unsupportive stakeholders to improve engagement - political awareness - cultural awareness (eg. One stakeholder doesn't appreciate the PM starting meeting with jokes, they may be OK with the format chosen eg. video conferencing, but may have other intangible issues)
Data representation: - stakeholder engagement matrix
Meetings
Manage communications
ensuring timely and appropriate collection, creation, distribution, storage, retrieval, monitoring and disposition of proj. info
I/P | T/T | O/P
Monitor communications
ensuring information needs of project and stakeholders are met
I/P | T/T | O/P
Proj mgmt plan - resource mgmt plan - communications mgmt plan - stakeholder engagement plan
Proj. docs - issue log - lessons learned register - project communications
Work performance data (types & quantities of data that have actually been distributed)
EEF (eg. Office politics culture, trends&habits)
OPA

## 8_PRSM
Non event risks
Variability risks - productivity may be lower or higher than expected, more # of defects may arise than normal etc. (can use monte carlo to address)
Ambuigity risks - ambiguity around elements of technical solution, future regulation changes etc. (can address by defining the knowledge gap and filling with external expert input or benchmarking)
Plan risk management
how to conduct risk mgmt activities for a project
ensures degree, type & visibility of risk mgmt is appropriate to both risks and the importance of the proj. to stakeholders and organization
I/P | T/T | O/P
Project charter (high level risks included here) | Expert judgment | Risk management plan - risk strategy - gen. approach - methodology - specific approaches used - roles & resp. - funding - establish protocol for application of contingency & mgmt reserve - timing - when risk mgmt will be carried out in proj. duration and incorporating those activities into proj. schedule - risk breakdown structure (eg. categorised as technical, commercial, management etc.) - stake holder risk appetite (risk thresholds) - definitions of risk probability and impacts (although specific to proj., it is a guide or 'look up table' for the user to assign a probabality and impact to a future risk) - probability & impact matrix - reporting format to be used and how tracking should be done
Proj mgmt plan - all components | Data analysis - stakeholder analysis (to determine risk appetite and assessment for resource allocation)
Proj. docs. - stakeholder register (mentions stakeholders' attitude towards risk on this project) | Meetings
EEF
OPA
Identify risks
I/P | T/T | O/P
Proj. mgmt plan - reqts. mgmt plan - schedule mgmt plan - cost mgmt plan - quality mgmt plan - resource mgmt plan - risk mgmt plan - scope baseline - schedule baseline - cost baseline
Proj. docs - assumption log - cost estimates - duration estimates - issue log - lessons learned register - reqts. documentation - resource requirements - stakeholder register
Agreements
Procurement Documentation
EEF
OPA
Perform qualitative risk analysis
prioritize individual project risks for further analysis/action by assessing their probability of occurrence 'AND' impact + other characteristics
subjective method, need to factor the risk attitude of the people involved in the analysis
I/P | T/T | O/P
Proj. mgmt plan - Risk mgmt plan | Expert judgment | Proj docs. Updates - Assumption log - Issue log - Risk register (eg. Updates of priority level/risk score) - classify risks placed on watch list vs. high priority risks - Risk report (prioritization of all identified risks on project with summary conclusion)
Proj. docs - assumption log - risk register - stakeholder register | Data gathering - interviews
EEF | Data analysis - Risk data quality assessment (how good is the quality of data on the indiv. project risks?) - Risk probability and impact assessment - Assessment of other risk parameters (urgency, proximity, dormancy, propinquity etc.)
OPA | Interpersonal and team skills - Facilitation
Risk categorization (laid out in the Risk mgmt plan)
Data representation - Probability and impact matrix (see 'definitions of risk probability and impacts' under risk mgmt plan for the numerical rating) - Hierarchical charts (when more than 2 parameters {> probability&impact} are used, eg. Bubble chart for 3 parameters)
Meetings
Perform quantitative risk analysis
numerically analyse combined effect of identified indiv. project risks and other uncertainty sources on overall proj. objectives
objective; time consuming; quantified probability of meeting project objectives; require specialized tools;
eg. assigning cost and schedule impacts to identified risks.
I/P | T/T | O/P
Proj. mgmt plan - Risk mgmt. plan - scope baseline - schedule baseline - cost baseline | Expert judgment | Project docs. Updates: Risk report - assessment of overall project risk exposure - detailed probabilistic analysis of the project (eg. S curves, tornado diagram o/p + narrative interpretation) - prioritized list of indiv. project risks - trends in quantitative risk analysis results - recommended risk responses
Proj. docs. - assumption log - basis of estimates - cost estimates - cost forecasts - duration estimates - milestone list - resource requirements - risk register - risk report - schedule forecasts | Data gathering (interviews)
EEF | Interpersonal and team skills (facilitation)
OPA (eg. Modeling software) | Representation of uncertainty (sources of distribution, prob dist. - triangular, normal, lognormal, beta etc.) Eg. Within a normal distribution, the likelihood of occurrence is noted within confidence intervals: 1Sigma, 2Sigma etc.
Data analysis - simulation eg. Monte carlo analysis: for cost risk - simulation uses cost estimates for schedule risk - simulation uses schedule network diagram + duration estimates - sensitivity analysis (eg. Tornado diagram - calculated correlation coefficient for each element of quant. risk analys. model) - decision tree analysis (eg. EMV calculation among different trees) - influence diagrams (graphical representation similar to S curve or Tornado diagram) NOTE: Net path value (Path 1) = Return on Investment A Path 1 - Cost of Investment A Path 1 Net path value (Path 2) = Return on Investment A Path 2 - Cost of Investment A Path 2 EMV = {Prob. x Net path value (Path 1)} + {Prob. x Net path value (Path 2)}
Plan risk responses
I/P | T/T | O/P
Proj. mgmt plan - resource mgmt plan - risk mgmt plan - cost baseline (has information on the contingency fund) | Expert judgment | Change requests
Proj. docs - lessons learned register - proj. schedule - proj. team assignments - resource calendars - risk register - risk report - stakeholder register | Data gathering (interviews) | Proj. mgmt plan updates - schedule mgmt plan - cost mgmt plan - quality mgmt plan - resource mgmt plan - procurement mgmt plan - scope baseline - schedule baseline - cost baseline
EEF (company culture, risk appetite, risk threshold) | Strategies for threats (Escalate, avoid - remove element of proj. and thus the asso. threat, transfer {contracts/insurance/warranties}, mitigate - pro-active, accept - prepare for contig. reserve, allot time {active}) | Proj. docs. updates - assumption log - cost forecasts (if planned risk responses entail additional costs) - lessons learned register - proj. schedule - proj. team assignments - risk register (updated risk responses, contingency plans, fallback plans, residual risks {left over risks after resp. is implemented}, secondary risks {direct undesired result of implemeting risk response} etc.) NOTE: risk register may also be updated for trigger conditions, symptoms, warning signs of risk occurence and appropriate response planned
OPA | Strategies for opportunities (Escalate, exploit, share, enhance - increase likelihood:proactive, accept)
Contingent response strategies (aka fallback plans) NOTE: contingency reserves set aside for one specific risk may not be used for another risk; If the original risk passes, the risk register should be updated accordingly and contingency reserves should be freed up (usually by a change request, because contingency reserves are part of cost baseline) NOTE: Cost savings realized during a project (from exploiting an opportunity) may be added to the contingency reserves, but BAC/cost baseline is not updated
Strategies for overall proj. risk (eg. Avoid - removing high-risk elements means canceling project)
Data analyses - alternatives analysis - cost-benefit analysis
Decision making (multi criteria decision analysis)
Implement risk responses
I/P | T/T | O/P
Change requests (eg. Change to scope, schedule or cost baseline) NOTE: when management reserves are used for 'unkown unknowns', the amount of money requested for that one particular risk response is now included in the cost baseline and this update to cost baseline is done through integrated change control.
Proj. docs. updates - issue log - lessons learned register - project team assignments - risk register - risk report
Monitor risks
monitoring implementation of agreed upon risk responses, their effectiveness, and identifying & analysing new risks (aka risk reassessment);
IMPORTANT DISTINCTION: this is a 'monitor' process, not a 'control' process, thus only the effectiveness of the risk responses are evaluated and occurrence of other new risks are monitored; There is 'NO' change to baselines or forecasts following this process, that only occurs as o/p of a 'control' process. Changes to proj. mgmt plan and proj. docs, however, can be expected even from a 'monitor' process.
I/P | T/T | O/P
Proj. mgmt plan - risk mgmt plan (eg. roles&resp., reporting format) | Data analysis - technical performance analysis (eg. weight, transaction time, # of defects) - reserve analysis (does the contingency reserve require modification, i.e. is the remaining reserve adequate? Is Schedule reserve time change needed?)
Proj. docs. - issue log - lessons learned register - risk register - risk report | Audits (eg. Risk audit: note this is an audit of the process, i.e., evaluate the effectiveness of the risk management process, not of the risk nor of the responses themselves)
Work performance data (risks that have occurred, risks active, closed out etc.) | Meetings (eg. risk review meetings: examines effectives of the risk responses themselves; New risks/issues identified are subsequently noted in the Issue log, i.e., risk reassessment)
Work performance reports (variance analysis, earned value data and forecasting data)

## 9_PPM
NOTE: All sellers for the project are stakeholders!
MSA (Master services agreements) used for fluid contracts requirement and need for ongoing seller involvement - useful in Agile environments
Plan procurement management
how to document project procurement decisions, how to approach and identify sellers
I/P | T/T | O/P
Proj. charter (obj., description, milestones, financial resources) | Expert judgment | Procurement mgmt plan - how procurement will be co-ordinated with other proj. aspects - timetable of key proc. activ. - procurement metrics to manage contracts - stakeholder resp. and roles related to proc. (eg. who is resp. for closing procurements?) - constraints and assump. affecting planned proc. - legal jursi. and currency of payments - determining whether independent estimates will be used - risk mgmt issues - is performance bond or insurance contract needed? - prequalified sellers, if any, to be used
Business documents - business case (procurement strategy and business case need to be aligned) - benefits mgmt plan (describers when specific project benefits will become available, which will drive procurement dates and contract language) | Data gathering (market research - examination of industry and spec. seller capabilities) | Procurement strategy - delivery methods (eg. construction: turnkey, design build, design bid build, build-own-operate-transfer) - contract payment types - procurement phases
Proj. mgmt plan - scope mgmt plan - quality mgmt plan (eg. Buidling codes, electrical specs., stds. etc) - resource mgmt plan (what roles, resp., skills are needed? Etc. are answered here) - scope baseline | Data analysis - Make or Buy analysis (payback period, ROI, internal rate of return, discounted cash flow, NPV, benefit/cost analysis (BCA)) | Bid documents (RFI, RFQ, RFP etc.)
| Source selection analysis - Least cost - qualifications only - quality based/highest technical proposal score - quality and cost based - sole source - fixed budget (buyer constrains sellers to a fixed budget in the RFP) | Procurement statement of work (SOW) - defines only that portion of the project scope that is to be included within the related contract; aka Terms of reference (TOR)
| Meetings | Source selection criteria (capabilty, capacity, product cost, delivery dates etc.) with scoring method and weighted criteria, if applicable
OPA (eg. Preapproved seller list; contract types:- - fixed price: firm fixed price, fixed price incentive fee, fixed price with economic price adjustments (buyers adjust fluctuating costs from eg. airline costs, currency shifts) - cost reimbursable contracts: cost plus fixed fee, cost plus incentive fee, cost plus award fee (based on a subjective buyer feel) - time & material contracts (hybrid of fixed price and cost-reimbursable) |  | Make or buy decisions (document the decision and update all relevant documents)
Independent cost estimates
Change requests
Proj. doc. Updates - lessons learned register - milestone list - requirements documentation - RTM - risk register - stakeholder register (eg. Inclusion of regulatory, contractual or legal personnel)
OPA updates (eg. Info on qualified sellers)
Conduct procurements
process of obtaining seller responses, selecting a seller and awarding a contract
NOTE: acquiring of independent contractors is an PRM: 'Acquire resources' process
I/P | T/T | O/P
Selected sellers
Agreements (could include contracts issued to certain sellers supplying complex goods/services) The following could be included: - Statement of work - schedules, milestones - performance reporting - pricing & payment terms - quality & acceptance - warranty & support - incentives & penalties - insurance bonds - subcontractor bonds - Terms & conditions - change request handling (eg. detailing of a contract change control system) - termination clause
Procurement documentation (bid documents, procurements SOW, independent cost estimates, supplier selection criteria) | Bidder conferences (conducted with shortlisted sellers and ensure clarifcations on work scope are given and everyone gets the same information)
EEF | Interpers. & team skills (negotiation) - Negotiations with seller are not lead by PM, but by purchasing/procurement team member designate, PM and team members only support; PM negotiates primarily with stakeholders (eg. Customers) | Proj. doc. Updates - lessons learned register - requirements documentation - requirements traceability matrix - resource calendars - risk register - stakeholder register (as new sellers are on board, they become new stakeholders) - do multiple team building events throughout project, involve key sellers as well.
OPA |  | OPA updates (eg. rates quoted from sellers etc.)
Control procurements
managing procurement relationships; monitoring contract performance and making changes as appropriate, and closing out contracts;
I/P | T/T | O/P
Closed procurements (a procurement administrator or similar resource would be the person to formally notify seller of contract completion, not the PM; PM and team members verify and approve deliverables Also typical practice is to keep procurement (or contract) open till activities are complete even at the expense of keeping project open Types of Contract Termination: - normal case - termination for cause - termination for convenience - right of termination - early termination - partial termination
Procurement documentation updates - changes to contracts - technical documentation - deliverables - seller reports and warranties - financial documents - contract-related inspections
Procurement documentation (bid documents, procurements SOW, independent cost estimates, supplier selection criteria) | Inspection (inspect seller deliverables)
Approved change requests (eg. change to contract terms, or change to SOW etc.) Seller can 'get well', i.e., negotiate for more favorable terms, once buyer redefines work scope (common occurrence at BW!) | Audits ("Trust, but verify! the procurement process and sellers)
Work performance data |  | Proj. documents updates - lessons learned register - resource requirements (changes to contractor work assignments may be needed as work progresses) - RTM (updated with info on reqts. that have been satisfied) - risk register - stakeholder register (new contractors/vendors onboarded or offboarded)
EEF (eg. Accounts payable system, Buyer's code of ethics) |  | OPA updates (eg. Seller performance evaluation documentation, prequalified seller lists updates, procurement file)
OPA

## 10_PSKM
Identify stakeholders
identifying project stakeholders 'regularly' and analysing&documenting their interests, interdependencies, potential impact on proj. success etc.
process of stakeholder identification and engagement should ideally begin as soon as proj. charter is approved, PM is assigned and team begins to form.
NOTE: under Tools&Techniques, 'Stakeholder Holder Analysis' is unique to the 'Identify Stakeholders' process, it is solely useful for evaluating who the stakeholders need to be;
I/P | T/T | O/P
Proj charter (has key stakeholder list) | Expert judgment | Stakeholder register - identification information (name, organisation, position, role on proj. etc.) - assessment information (major reqts/expectations, potential for influencing proj. outcomes, and phase of proj. where influence is greatest) - stakhldr. classification information (int./ext., impact/infl/power/interest, upward/outward/downward/sideward) Note: charter contains only high level stakeholders identified initially, any new stakholders identified dont get added to charter, but to the register)
Business docs - business case (initial list of stkhols. affected by proj.) - benefits mgmt plan (identify invid. who will benefit from delievery of outcomes and are thus stakeholders) | Data gathering - Questionnaires & surveys - Brainstorming - Brainwriting (individual time with questions provided beforehand before convening as group) | Change requests (not for first iteration, but for future iterations of change to stakeholder register)
Proj. mgmt plan - comm. mgmt plan (has stakeholder comm. reqts.) - stakeholder engagement plan | Data analysis - Stakeholder analysis (stakes include: interests, rights, ownership, knowledge, contribution): *help understand environment *reveal interests *anticipate potential conflict and risk *identify champions and challengers *leverage relationships - Document analysis | Proj. mgmt plan updates (for further iterations) - requirements mgmt. plan (new stkhldrs. or change to stkhldrs. may cause new requirements) - comm. mgmt. plan - risk mgmt. plan - stakehldr. engn. plan
Proj. docs. - change log (may introduce new stakhldr., or change relationship of existing one) - issue log - reqts. documentation | Data representation - Power/interest grid or Power/influence grid or Impact/influence grid (grouping of stakeholders according to level of authority, level of concern, ability to influence, ability to cause changes) - Stakeholder cube - 3-D rep of the previously described grid - Salience model (classes of stkhldrs. based on assessments of their power, urgency and legitimacy - used for larger/complex networks) - Directions of influence (upward, downward, outward, sideward) - Prioritization | Proj. docs. Updates - assumption log (assumptions on stakholds power, influ. etc.) - issue log - risk register
Agreements (parties of agreements are stkholds.) | Meetings
EEF (eg. Govt standards or regs.)
OPA
Plan stakeholder Management
developing approaches (how?) to involve stkhldrs. based on their needs, expectations, potential impact on project
I/P | T/T | O/P
Manage stakeholder engagement
communicating and working with stakeholders to meet needs, address issues
I/P | T/T | O/P
Change requests (eg. Changes to project/product scope)
Proj. mgmt plan updates - communications management plan - stakeholder engagement plan
Proj. docs. Updates - change log - issue log (Note when some issue comes along and as result stakeholder enagagement is 'expected' to wane or 'does start' to wane, before updating the stakeholder engn. assessment matrix or the engn. plan., first update the concern in the issue log) - lessons register (eg. Eff./ineff. approaches) - stakeholder register
Monitor stakeholder engagement
monitoring stkhldr. relationships and tailoring strategies for re-engaging where necessary
I/P | T/T | O/P
Proj. mgmt plan - resource mgmt plan - comm. mgmt plan - stakehldr. engn. plan |  | Work performance information (eg. current vs. desired level of project support/engagement)
Proj. docs - issue log - lessons learned register - project communications (these are the ones that have already been issued to stkhldrs.) - risk register - stakhldr. register |  | Change requests
Work performance data (the data can help answer which stkhldrs. are supportive of the project) - attendance, assignment status, action/resp. - agg. polling, grids/cube, demo feedback |  | Proj. mgmt plan updates - resource mgmt plan (team responsibilities for stakeholder engagement activities needing to be updated) - comm. mgmt plan - stkhldr. engn. plan
EEF |  | Proj. docs. updates (notice change log is not included here, why? Because changes resulting from the 'Monitoring' process usually only affects the 'HOW', i.e., the proj. mgmt plans) - issue log - lessons learned register (eg. Eff./ineff. approaches) - risk register - stakeholder register (adjust power, influence, interest and include new stkhldrs.)
OPA (social media, ethics & security) | Interpersonal and team skills - active listening - cultural awareness - leadership - networking - political awareness
Meetings