## Mind Map
Legend
| Inititaing Process | Process occurs in Initiating Process Group
| Plannning Process | Process occurs in Planning Process Group
| Executing Process | Process occurs in Executing Process Group
| Monitoring and Controlling Process | Process occurs in Monitoring & Controlling Process Group
| Closing process | Process occurs in Closing Process Group
| Unique Input | Appears as an input in only one process eg Project Statement of Work is an input to only Develop Project Charter. Doesn’t appear anywhere else in ITTO
| Input - Output (One to One relationship) | Output from a process which is an input to only 1 process eg Deliverables ( Output from only Direct & manage Project Work and Input to only Control Quality). Basically appears only twice in ITTO, once as an output and once as an input
| Unique T&T | Appears as a T&T in only one process eg Interviews are Tools & Techniques for only Collect Requirements. Doesn't appear anywhere else in ITTO
| Unique Output | Appears as an output in only one process eg Final Product/Service/result Transition is an output of only Close Project/Phase. Doesn’t appear anywhere else in ITTO
| Remark | The sequence of Items inside Inputs, T&T and Output may vary from what mentioned in PMBOK . I have sequenced them in order of their appearance in the ITTO table. For eg if an Input contains PMP and Project Charter , Project charter will always appear above PMP as Project Charter is the output of 1st process itself.
| Comments | Comments have been added to many cells particularly T&T items to elaborate and list down subcomponents. Eg the comment of 7 basic Quality tools lists the names of 7 tools
Project Integration Management
| Develop Project Charter |  |  | Develop PMP |  |  | Direct & Manage Project work |  |  | Monitor & Control Project work |  |  | Perform Integrated Change Control |  |  | Close Project or Phase
| Develop Project Charter | Inputs |  | Develop PMP | Inputs |  | Direct & Manage Project work | Inputs |  | Monitor & Control Project work | Inputs |  | Perform Integrated Change Control | Inputs |  | Close Project or Phase | Inputs
| Develop Project Charter | 1 | Project Statement of Work | Develop PMP | 1 | Project Charter | Direct & Manage Project work | 1 | PMP | Monitor & Control Project work | 1 | PMP | Perform Integrated Change Control | 1 | PMP | Close Project or Phase | 1 | PMP
| Develop Project Charter | 2 | Business Case | Develop PMP | 2 | Outputs from other processes | Direct & Manage Project work | 2 | Approved Change Requests | Monitor & Control Project work | 2 | WPI | Perform Integrated Change Control | 2 | WPR | Close Project or Phase | 2 | Accepted Deliverables
| Develop Project Charter | 3 | Agreements | Develop PMP | 3 | EEF | Direct & Manage Project work | 3 | EEF | Monitor & Control Project work | 3 | Schedule Forecasts | Perform Integrated Change Control | 3 | Change Requests | Close Project or Phase | 3 | OPA
| Develop Project Charter | 4 | EEF | Develop PMP | 4 | OPA | Direct & Manage Project work | 4 | OPA | Monitor & Control Project work | 4 | Cost Forecasts | Perform Integrated Change Control | 4 | EEF | Close Project or Phase | T&T
| Develop Project Charter | 5 | OPA | Develop PMP | T&T |  | Direct & Manage Project work | T&T |  | Monitor & Control Project work | 5 | Validated Changes | Perform Integrated Change Control | 5 | OPA | Close Project or Phase | 1 | EJ
| Develop Project Charter | T&T |  | Develop PMP | 1 | EJ | Direct & Manage Project work | 1 | EJ | Monitor & Control Project work | 6 | EEF | Perform Integrated Change Control | T&T |  | Close Project or Phase | 2 | Meetings
| Develop Project Charter | 1 | EJ | Develop PMP | 2 | Facilitation Techniques | Direct & Manage Project work | 2 | PMIS | Monitor & Control Project work | 7 | OPA | Perform Integrated Change Control | 1 | EJ | Close Project or Phase | 3 | Analytical Techniques
| Develop Project Charter | 2 | Facilitation Techniques | Develop PMP | Outputs |  | Direct & Manage Project work | 3 | Meetings | Monitor & Control Project work | T&T |  | Perform Integrated Change Control | 2 | Meetings | Close Project or Phase | Outputs
| Develop Project Charter | Outputs |  | Develop PMP | 1 | PMP | Direct & Manage Project work | Outputs |  | Monitor & Control Project work | 1 | EJ | Perform Integrated Change Control | 3 | Change Control tools | Close Project or Phase | 1 | Final Product/Service/result Transition
| Develop Project Charter | 1 | Project Charter |  |  |  | Direct & Manage Project work | 1 | Deliverables | Monitor & Control Project work | 2 | PMIS | Perform Integrated Change Control | Outputs |  | Close Project or Phase | 2 | OPA updates
[7 empty] | Direct & Manage Project work | 2 | WPD | Monitor & Control Project work | 3 | Meetings | Perform Integrated Change Control | 1 | Approved Change Requests
[7 empty] | Direct & Manage Project work | 3 | Change Requests | Monitor & Control Project work | 4 | Analytical Techniques | Perform Integrated Change Control | 2 | Change Log
[7 empty] | Direct & Manage Project work | 4 |  | Monitor & Control Project work | Outputs |  | Perform Integrated Change Control | 3 | PMP Updates
[7 empty] | Direct & Manage Project work | 5 | PMP updates | Monitor & Control Project work | 1 | WPR | Perform Integrated Change Control | 4 | PD Updates
[9 empty] | PD updates | Monitor & Control Project work | 2 | Change Requests
[10 empty] | Monitor & Control Project work | 3 | PMP Updates
[10 empty] | Monitor & Control Project work | 4 | PD Updates
Project Scope Management
| Plan Scope Management |  |  | Collect requirements |  |  | Define Scope |  |  | Create WBS |  |  | Validate Scope |  |  | Control Scope
| Plan Scope Management | Inputs |  | Collect requirements | Inputs |  | Define Scope | Inputs |  | Create WBS | Inputs |  | Validate Scope | Inputs |  | Control Scope | Inputs
| Plan Scope Management | 1 | Project Charter | Collect requirements | 1 | Project Charter | Define Scope | 1 | Project Charter | Create WBS | 1 | Scope MP | Validate Scope | 1 | PMP | Control Scope | 1 | PMP
| Plan Scope Management | 2 | PMP | Collect requirements | 2 | Scope MP | Define Scope | 2 | Scope MP | Create WBS | 2 | Requirements Documentation | Validate Scope | 2 | WPD | Control Scope | 2 | WPD
| Plan Scope Management | 3 | EEF | Collect requirements | 3 | Requirements MP | Define Scope | 3 | Requirements Documentation | Create WBS | 3 | PSS | Validate Scope | 3 | Requirements Documentation | Control Scope | 3 | Requirements Documentation
| Plan Scope Management | 4 | OPA | Collect requirements | 4 | Stakeholder Register | Define Scope | 4 | OPA | Create WBS | 4 | EEF | Validate Scope | 4 | RTM | Control Scope | 4 | RTM
| Plan Scope Management | T&T |  | Collect requirements | 5 | Stakeholder MP | Define Scope | T&T |  | Create WBS | 5 | OPA | Validate Scope | 5 | Verified Deliverables | Control Scope | 5 | OPA
| Plan Scope Management | 1 | EJ | Collect requirements | T&T |  | Define Scope | 1 | EJ | Create WBS | T&T |  | Validate Scope | T&T |  | Control Scope | T&T
| Plan Scope Management | 2 | Meetings | Collect requirements | 1 | Interviews | Define Scope | 2 | Facilitated Workshops | Create WBS | 1 | EJ | Validate Scope | 1 | Inspection | Control Scope | 1 | Variance Analysis
| Plan Scope Management | Outputs |  | Collect requirements | 2 | Focus Groups | Define Scope | 3 | Products Analysis | Create WBS | 2 | Decomposition | Validate Scope | 2 | GDMT | Control Scope | Outputs
| Plan Scope Management | 1 | Scope MP | Collect requirements | 3 | Facilitated Workshops | Define Scope | 4 | Alternatives Generation | Create WBS | Outputs |  | Validate Scope | Outputs |  | Control Scope | 1 | WPI
| Plan Scope Management | 2 | Requirements MP | Collect requirements | 4 | GCT | Define Scope | Outputs |  | Create WBS | 1 | Scope Baseline | Validate Scope | 1 | Accepted Deliverables | Control Scope | 2 | Change Requests
|  |  |  | Collect requirements | 5 | GDMT | Define Scope | 1 | PSS | Create WBS | 2 | PD Updates | Validate Scope | 2 | WPI | Control Scope | 3 | PMP Updates
|  |  |  | Collect requirements | 6 | Questionnaires & Surveys | Define Scope | 2 | PD updates |  |  |  | Validate Scope | 3 | Change Requests | Control Scope | 4 | PD Updates
|  |  |  | Collect requirements | 7 | Observations | [6 empty] | Validate Scope | 4 | PD Updates | Control Scope | 5 | OPA updates
|  |  |  | Collect requirements | 8 | Prototypes
|  |  |  | Collect requirements | 9 | Benchmarking
|  |  |  | Collect requirements | 10 | Context Diagrams
|  |  |  | Collect requirements | 11 | Document Analysis
|  |  |  | Collect requirements | Output
|  |  |  | Collect requirements | 1 | Requirements Documentation
|  |  |  | Collect requirements | 2 | RTM
Project Time Management
| Plan Schedule Management |  |  | Define Activities |  |  | Sequence Activities |  |  | Estimate Activity Resources |  |  | Estimate Activity Durations |  |  | Develop Schedule |  |  | Control Schedule
| Plan Schedule Management | Inputs |  | Define Activities | Inputs |  | Sequence Activities | Inputs |  | Estimate Activity Resources | Inputs |  | Estimate Activity Durations | Inputs |  | Develop Schedule | Inputs |  | Control Schedule | Inputs
| Plan Schedule Management | 1 | Project Charter | Define Activities | 1 | Scope Baseline | Sequence Activities | 1 | PSS | Estimate Activity Resources | 1 | Schedule MP | Estimate Activity Durations | 1 | PSS | Develop Schedule | 1 | PSS | Control Schedule | 1 | PMP
| Plan Schedule Management | 2 | PMP | Define Activities | 2 | Schedule MP | Sequence Activities | 2 | Schedule MP | Estimate Activity Resources | 2 | Activity List | Estimate Activity Durations | 2 | Schedule MP | Develop Schedule | 2 | Schedule MP | Control Schedule | 2 | WPD
| Plan Schedule Management | 3 | EEF | Define Activities | 3 | EEF | Sequence Activities | 3 | Activity List | Estimate Activity Resources | 3 | Activity Attributes | Estimate Activity Durations | 3 | Activity List | Develop Schedule | 3 | Activity List | Control Schedule | 3 | Project Schedule
| Plan Schedule Management | 4 | OPA | Define Activities | 4 | OPA | Sequence Activities | 4 | Activity Attributes | Estimate Activity Resources | 4 | Activity Cost Estimates | Estimate Activity Durations | 4 | Activity Attributes | Develop Schedule | 4 | Activity Attributes | Control Schedule | 4 | Schedule Data
| Plan Schedule Management | T&T |  | Define Activities | T&T |  | Sequence Activities | 5 | Milestone List | Estimate Activity Resources | 5 | Resource Calendar | Estimate Activity Durations | 5 | Activity Resource Requirements | Develop Schedule | 5 | PSND | Control Schedule | 5 | Project Calendars
| Plan Schedule Management | 1 | EJ | Define Activities | 1 | EJ | Sequence Activities | 6 | EEF | Estimate Activity Resources | 6 | Risk Register | Estimate Activity Durations | 6 | RBS | Develop Schedule | 6 | Activity resource requirements | Control Schedule | 6 | OPA
| Plan Schedule Management | 2 | Meetings | Define Activities | 2 | Decomposition | Sequence Activities | 7 | OPA | Estimate Activity Resources | 7 | EEF | Estimate Activity Durations | 7 | Resource Calendars | Develop Schedule | 7 | RBS | Control Schedule | T&T
| Plan Schedule Management | 3 | Analytical techniques | Define Activities | 3 | Rolling Wave Planning | Sequence Activities | T&T |  | Estimate Activity Resources | 8 | OPA | Estimate Activity Durations | 8 | Risk Register | Develop Schedule | 8 | Activity DuratioN Estimates | Control Schedule | 1 | Performance Reviews
| Plan Schedule Management | Outputs |  | Define Activities | Outputs |  | Sequence Activities | 1 | PDM | Estimate Activity Resources | T&T |  | Estimate Activity Durations | 9 | EEF | Develop Schedule | 9 | Project Staff Assignments | Control Schedule | 2 | PMS
| Plan Schedule Management | 1 | Schedule MP | Define Activities | 1 | Activity List | Sequence Activities | 2 | Dependancy Determination | Estimate Activity Resources | 1 | EJ | Estimate Activity Durations | 10 | OPA | Develop Schedule | 10 | Resource Calendars | Control Schedule | 3 | Resource Optimisation Techniques
|  |  |  | Define Activities | 2 | Activity Attributes | Sequence Activities | 3 | L&L | Estimate Activity Resources | 2 | Alternatives Analysis | Estimate Activity Durations | T&T |  | Develop Schedule | 11 | Risk Register | Control Schedule | 4 | Modelling Techniques
|  |  |  | Define Activities | 3 | Milestone List | Sequence Activities | Outputs |  | Estimate Activity Resources | 3 | Published Estimating Data | Estimate Activity Durations | 1 | EJ | Develop Schedule | 12 | EEF | Control Schedule | 5 | L&L
[7 empty] | Sequence Activities | 1 | PSND | Estimate Activity Resources | 4 | Bottom-up Estimating | Estimate Activity Durations | 2 | Analogous Estimating | Develop Schedule | 13 | OPA | Control Schedule | 6 | Schedule Compression
[7 empty] | Sequence Activities | 2 | PD Updates | Estimate Activity Resources | 5 | PMS | Estimate Activity Durations | 3 | Parametric Estimating | Develop Schedule | T&T |  | Control Schedule | 7 | Scheduling Tools
[10 empty] | Estimate Activity Resources | Outputs |  | Estimate Activity Durations | 4 | 3 point estimating | Develop Schedule | 1 | Schedule Network Analysis | Control Schedule | Outputs
[10 empty] | Estimate Activity Resources | 1 | Activity Resource requirements | Estimate Activity Durations | 5 | GDMT | Develop Schedule | 2 | CPM | Control Schedule | 1 | Schedule Forecasts
[10 empty] | Estimate Activity Resources | 2 | RBS | Estimate Activity Durations | 6 | Reserve Analysis | Develop Schedule | 3 | CCM | Control Schedule | 2 | WPI
[10 empty] | Estimate Activity Resources | 3 | PD Updates | Estimate Activity Durations | Outputs |  | Develop Schedule | 4 | Resource Optimisation Techniques | Control Schedule | 3 | Change Requests
[13 empty] | Estimate Activity Durations | 1 | Actvity Duration Estimates | Develop Schedule | 5 | Modelling Techniques | Control Schedule | 4 | PMP Updates
[13 empty] | Estimate Activity Durations | 2 | PD Updates | Develop Schedule | 6 | L&L | Control Schedule | 5 | PD Updates
[16 empty] | Develop Schedule | 7 | Schedule Compression | Control Schedule | 6 | OPA Updates
[16 empty] | Develop Schedule | 8 | Scheduling Tools
[16 empty] | Develop Schedule | Outputs
[16 empty] | Develop Schedule | 1 | Schedule Baseline
[16 empty] | Develop Schedule | 2 | Project Schedule
[16 empty] | Develop Schedule | 3 | Schedule Data
[16 empty] | Develop Schedule | 4 | Project Calendars
[16 empty] | Develop Schedule | 5 | PMP Updates
[16 empty] | Develop Schedule | 6 | PD Updates
Project Cost Management
| Plan Cost Management |  |  | Estimate Costs |  |  | Determine Budget |  |  | Control Costs
| Plan Cost Management | Inputs |  | Estimate Costs | Inputs |  | Determine Budget | Inputs |  | Control Costs | Inputs
| Plan Cost Management | 1 | Project Charter | Estimate Costs | 1 | Scope Baseline | Determine Budget | 1 | Scope Baseline | Control Costs | 1 | PMP
| Plan Cost Management | 2 | PMP | Estimate Costs | 2 | Project Schedule | Determine Budget | 2 | Project Schedule | Control Costs | 2 | WPD
| Plan Cost Management | 3 | EEF | Estimate Costs | 3 | Cost MP | Determine Budget | 3 | Cost MP | Control Costs | 3 | PFR
| Plan Cost Management | 4 | OPA | Estimate Costs | 4 | Human Resource MP | Determine Budget | 4 | Activity Cost estimates | Control Costs | 4 | OPA
| Plan Cost Management | T&T |  | Estimate Costs | 5 | Risk register | Determine Budget | 5 | Basis of Estimates | Control Costs | T&T
| Plan Cost Management | 1 | EJ | Estimate Costs | 6 | EEF | Determine Budget | 6 | Resource Calendars | Control Costs | 1 | Performance reviews
| Plan Cost Management | 2 | Meetings | Estimate Costs | 7 | OPA | Determine Budget | 7 | Risk register | Control Costs | 2 | PMS
| Plan Cost Management | 3 | Analytical Techniques | Estimate Costs | T&T |  | Determine Budget | 8 | EEF | Control Costs | 3 | Reserve Analysis
| Plan Cost Management | Outputs |  | Estimate Costs | 1 | EJ | Determine Budget | 9 | OPA | Control Costs | 4 | EVM
| Plan Cost Management | 1 | Cost MP | Estimate Costs | 2 | Bottom-up Estimating | Determine Budget | T&T |  | Control Costs | 5 | Forecasting
|  |  |  | Estimate Costs | 3 | PMS | Determine Budget |  | EJ | Control Costs | 6 | TCPI
|  |  |  | Estimate Costs | 4 | Analogous Estimating | Determine Budget |  | Reserve Analysis | Control Costs | Outputs
|  |  |  | Estimate Costs | 5 | Parametric Estimating | Determine Budget |  | Cost Aggregation | Control Costs | 1 | Cost Forecasts
|  |  |  | Estimate Costs | 6 | 3 Point estimating | Determine Budget |  | Historical Relationships | Control Costs | 2 | WPI
|  |  |  | Estimate Costs | 7 | GDMT | Determine Budget |  | Funding Limit Reconciliation | Control Costs | 3 | Change Requests
|  |  |  | Estimate Costs | 8 | Reserve Analysis | Determine Budget | Outputs |  | Control Costs | 4 | PMP Updates
|  |  |  | Estimate Costs | 9 | Cost Of Quality | Determine Budget |  | Cost Baseline | Control Costs | 5 | PD Updates
|  |  |  | Estimate Costs | 10 | Vendor Bid Analysis | Determine Budget |  | PFR | Control Costs | 6 | OPA Updates
|  |  |  | Estimate Costs | Outputs |  | Determine Budget |  | PD Updates
|  |  |  | Estimate Costs | 1 | Activity Cost Estimates
|  |  |  | Estimate Costs | 2 | Basis of Estimates
|  |  |  | Estimate Costs | 3 | PD Updates
Project Quality Management
| Plan Quality Management |  |  | Perform Quality Assurance |  |  | Control Quality
| Plan Quality Management | Inputs |  | Perform Quality Assurance | Inputs |  | Control Quality | Inputs
| Plan Quality Management | 1 | PMP | Perform Quality Assurance | 1 | Quality MP | Control Quality | 1 | PMP
| Plan Quality Management | 2 | Requirements Documentation | Perform Quality Assurance | 2 | Process Improvement Plan | Control Quality | 2 | Deliverables
| Plan Quality Management | 3 | Risk Register | Perform Quality Assurance | 3 | QualitY Metrics | Control Quality | 3 | WPD
| Plan Quality Management | 4 | Stakeholder Register | Perform Quality Assurance | 4 | Quality Control Measurements | Control Quality | 4 | Approved Change Requests
| Plan Quality Management | 5 | EEF | Perform Quality Assurance | 5 | PD | Control Quality | 5 | Quality Metrics
| Plan Quality Management | 6 | OPA | Perform Quality Assurance | T&T |  | Control Quality | 6 | Quality Checklists
| Plan Quality Management | T&T |  | Perform Quality Assurance | 1 | Quality Management & Control Tools | Control Quality | 7 | PD
| Plan Quality Management | 1 | Meetings | Perform Quality Assurance | 2 | Quality audits | Control Quality | 8 | OPA
| Plan Quality Management | 2 | Cost-Benefit Analysis | Perform Quality Assurance | 3 | Process Analysis | Control Quality | T&T
| Plan Quality Management | 3 | Cost Of Quality | Perform Quality Assurance | Outputs |  | Control Quality | 1 | Inspection
| Plan Quality Management | 4 | 7 Basic Quality Tools | Perform Quality Assurance | 1 | Change requests | Control Quality | 2 | 7 Basic Quality Tools
| Plan Quality Management | 5 | Benchmarking | Perform Quality Assurance | 2 | PMP Updates | Control Quality | 3 | Statistical Sampling
| Plan Quality Management | 6 | Design of Experiments | Perform Quality Assurance | 3 | PD updates | Control Quality | 4 | Approved Change Requests Review
| Plan Quality Management | 7 | Statistical Sampling | Perform Quality Assurance | 4 | OPA Updates | Control Quality | Outputs
| Plan Quality Management | 8 | Additional Quality Planning Tools |  |  |  | Control Quality | 1 | Quality Control Measurements
| Plan Quality Management | Outputs |  |  |  |  | Control Quality | 2 | Validated Changes
| Plan Quality Management | 1 | Quality MP |  |  |  | Control Quality | 3 | Verified Deliverables
| Plan Quality Management | 2 | Process Improvement Plan |  |  |  | Control Quality | 4 | WPI
| Plan Quality Management | 3 | QualitY Metrics |  |  |  | Control Quality | 5 | Change Requests
| Plan Quality Management | 4 | Quality Checklists |  |  |  | Control Quality | 6 | PMP Updates
| Plan Quality Management | 5 | PD Updates |  |  |  | Control Quality | 7 | PD Updates
[7 empty] | Control Quality | 8 | OPA Updates
Project HR Management
| Plan HR Management |  |  | Acquire Project Team |  |  | Develop Project Team |  |  | Manage Project Team
| Plan HR Management | Inputs |  | Acquire Project Team | Inputs |  | Develop Project Team | Inputs |  | Manage Project Team | Inputs
| Plan HR Management | 1 | PMP | Acquire Project Team | 1 | HR MP | Develop Project Team | 1 | HR MP | Manage Project Team | 1 | WPR
| Plan HR Management | 2 | Activity Resource Requirements | Acquire Project Team | 2 | EEF | Develop Project Team | 2 | Project Staff Assignemnts | Manage Project Team | 2 | HR MP
| Plan HR Management | 3 | EEF | Acquire Project Team | 3 | OPA | Develop Project Team | 3 | Resource Calendars | Manage Project Team | 3 | Project Staff Assignments
| Plan HR Management | 4 | OPA | Acquire Project Team | T&T |  | Develop Project Team | T&T |  | Manage Project Team | 4 | Team Performance Assessment
| Plan HR Management | T&T |  | Acquire Project Team | 1 | Pre-Assignment | Develop Project Team | 1 | Interpersonal skills | Manage Project Team | 5 | Issue Log
| Plan HR Management | 1 | EJ | Acquire Project Team | 2 | Negotiation | Develop Project Team | 2 | Training | Manage Project Team | 6 | OPA
| Plan HR Management | 2 | Meetings | Acquire Project Team | 3 | Acquisition | Develop Project Team | 3 | Team-Building Activities | Manage Project Team | T&T
| Plan HR Management | 3 | Organisational Charts & Position Descriptions | Acquire Project Team | 4 | Virtual teams | Develop Project Team | 4 | Ground Rules | Manage Project Team | 1 | Interpersonal skills
| Plan HR Management | 4 | Networking | Acquire Project Team | 5 | Multi Criteria Decision analysis | Develop Project Team | 5 | Co-Location | Manage Project Team | 2 | Observation & conversations
| Plan HR Management | 5 | Organisational Theory | Acquire Project Team | Outputs |  | Develop Project Team | 6 | Recognition & Rewards | Manage Project Team | 3 | Project Performance Appraisals
| Plan HR Management | Outputs |  | Acquire Project Team | 1 | Project Staff Assignemnts | Develop Project Team | 7 | Personnel Assessment Tools | Manage Project Team | 4 | Conflict Management
| Plan HR Management | 1 | HR MP | Acquire Project Team | 2 | Resource Calendars | Develop Project Team | Outputs |  | Manage Project Team | Outputs
|  |  |  | Acquire Project Team | 3 | PMP Updates | Develop Project Team | 1 | Team Performance Assessments | Manage Project Team | 1 | Change requests
[7 empty] | Develop Project Team | 2 | EEF Updates | Manage Project Team | 2 | PMP Updates
[10 empty] | Manage Project Team | 3 | PD Updates
[10 empty] | Manage Project Team | 4 | OPA Updates
[10 empty] | Manage Project Team | 5 | EEF updates
Project Communications Management
| Plan Communications Management |  |  | Manage Communications |  |  | Control Communications
| Plan Communications Management | Inputs |  | Manage Communications | Inputs |  | Control Communications | Inputs
| Plan Communications Management | 1 | PMP | Manage Communications | 1 | WPR | Control Communications | 1 | PMP
| Plan Communications Management | 2 | Stakeholder Register | Manage Communications | 2 | Communications MP | Control Communications | 2 | WPD
| Plan Communications Management | 3 | EEF | Manage Communications | 3 | EEF | Control Communications | 3 | Project Communications
| Plan Communications Management | 4 | OPA | Manage Communications | 4 | OPA | Control Communications | 4 | Issue Log
| Plan Communications Management | T&T |  | Manage Communications | T&T |  | Control Communications | 5 | OPA
| Plan Communications Management | 1 | Meetings | Manage Communications | 1 | Communication Technology | Control Communications | T&T
| Plan Communications Management | 2 | Communications Requirement Analysis | Manage Communications | 2 | Communication models | Control Communications | 1 | EJ
| Plan Communications Management | 3 | Communication Technology | Manage Communications | 3 | Communication Methods | Control Communications | 2 | Meetings
| Plan Communications Management | 4 | Communication models | Manage Communications | 4 | Information Management System | Control Communications | 3 | Information Management Systems
| Plan Communications Management | 5 | Communication Methods | Manage Communications | 5 | Performance Reporting | Control Communications | Outputs
| Plan Communications Management | Outputs |  | Manage Communications | Outputs |  | Control Communications | 1 | WPI
| Plan Communications Management | 1 | Communications MP | Manage Communications | 1 | Project Communications | Control Communications | 2 | Change Requests
| Plan Communications Management | 2 | PD Updates | Manage Communications | 2 | PMP Updates | Control Communications | 3 | PMP Updates
|  |  |  | Manage Communications | 3 | PD Updates | Control Communications | 4 | PD Updates
|  |  |  | Manage Communications | 4 | OPA Updates | Control Communications | 5 | OPA Updates
Project Risk Management
| Plan Risk Management |  |  | Identify Risks |  |  | Perform Qualitative Risk Analysis |  |  | Perform Quantitiave Risk Analysis |  |  | Plan Risk Responses |  |  | Control Risks
| Plan Risk Management | Inputs |  | Identify Risks | Inputs |  | Perform Qualitative Risk Analysis | Inputs |  | Perform Quantitiave Risk Analysis | Inputs |  | Plan Risk Responses | Inputs |  | Control Risks | Inputs
| Plan Risk Management | 1 | Project Charter | Identify Risks | 1 | Scope Baseline | Perform Qualitative Risk Analysis | 1 | Scope Baseline | Perform Quantitiave Risk Analysis | 1 | Schedule MP | Plan Risk Responses | 1 | Risk MP | Control Risks | 1 | PMP
| Plan Risk Management | 2 | PMP | Identify Risks | 2 | Schedule MP | Perform Qualitative Risk Analysis | 2 | Risk MP | Perform Quantitiave Risk Analysis | 2 | Cost MP | Plan Risk Responses | 2 | Risk Register | Control Risks | 2 | WPD
| Plan Risk Management | 3 | Stakeholder Register | Identify Risks | 3 | Activity Duration Estimates | Perform Qualitative Risk Analysis | 3 | Risk register | Perform Quantitiave Risk Analysis | 3 | Risk MP | Plan Risk Responses | T&T |  | Control Risks | 3 | WPR
| Plan Risk Management | 4 | EEF | Identify Risks | 4 | Cost MP | Perform Qualitative Risk Analysis | 4 | EEF | Perform Quantitiave Risk Analysis | 4 | Risk Register | Plan Risk Responses | 1 | EJ | Control Risks | 4 | Risk register
| Plan Risk Management | 5 | OPA | Identify Risks | 5 | Activity Cost Estimates | Perform Qualitative Risk Analysis | 5 | OPA | Perform Quantitiave Risk Analysis | 5 | EEF | Plan Risk Responses | 2 | Strategies for negative risks or threats | Control Risks | T&T
| Plan Risk Management | T&T |  | Identify Risks | 6 | Quality MP | Perform Qualitative Risk Analysis | T&T |  | Perform Quantitiave Risk Analysis | 6 | OPA | Plan Risk Responses | 3 | Strategies for positive risks or opportunities | Control Risks | 1 | Meetings
| Plan Risk Management | 1 | EJ | Identify Risks | 7 | HR MP | Perform Qualitative Risk Analysis | 1 | EJ | Perform Quantitiave Risk Analysis | T&T |  | Plan Risk Responses | 4 | Contingent Response Strategies | Control Risks | 2 | Reserve Analysis
| Plan Risk Management | 2 | Meetings | Identify Risks | 8 | Risk MP | Perform Qualitative Risk Analysis | 2 | Risk Probability and Impact Assessment | Perform Quantitiave Risk Analysis | 1 | EJ | Plan Risk Responses | Outputs |  | Control Risks | 3 | Risk Reassessment
| Plan Risk Management | 3 | Analytical Techniques | Identify Risks | 9 | Procurement Documents | Perform Qualitative Risk Analysis | 3 | Probability & Impact Matrix | Perform Quantitiave Risk Analysis | 2 | Data gathering & Representation Techniques | Plan Risk Responses | 1 | PMP Updates | Control Risks | 4 | Risk Audits
| Plan Risk Management | Outputs |  | Identify Risks | 10 | Stakeholder Register | Perform Qualitative Risk Analysis | 4 | Risk Data Quality Assessment | Perform Quantitiave Risk Analysis | 3 | Quantitative Risk Analysis & Modeling techniques | Plan Risk Responses | 2 | PD Updates | Control Risks | 5 | Variance & Trend Analysis
| Plan Risk Management | 1 | Risk MP | Identify Risks | 11 | PD | Perform Qualitative Risk Analysis | 5 | Risk Categorization | Perform Quantitiave Risk Analysis | Outputs |  |  |  |  | Control Risks | 6 | Technical Performance Measurement
|  |  |  | Identify Risks | 12 | EEF | Perform Qualitative Risk Analysis | 6 | Risk Urgency Assessment | Perform Quantitiave Risk Analysis | 1 | PD Updates |  |  |  | Control Risks | Outputs
|  |  |  | Identify Risks | 13 | OPA | Perform Qualitative Risk Analysis | Outputs | [7 empty] | Control Risks | 1 | WPI
|  |  |  | Identify Risks | T&T |  | Perform Qualitative Risk Analysis | 1 | PD Updates | [6 empty] | Control Risks | 2 | Change Requests
|  |  |  | Identify Risks | 1 | EJ | [9 empty] | Control Risks | 3 | PMP Updates
|  |  |  | Identify Risks | 2 | Documentation Reviews | [9 empty] | Control Risks | 4 | PD Updates
|  |  |  | Identify Risks | 3 | Information Gathering Techniques | [9 empty] | Control Risks | 5 | OPA Updates
|  |  |  | Identify Risks | 4 | Checklist Analysis
|  |  |  | Identify Risks | 5 | Assumptions Analysis
|  |  |  | Identify Risks | 6 | Diagramming Techniques
|  |  |  | Identify Risks | 7 | SWOT Analysis
|  |  |  | Identify Risks | Outputs
|  |  |  | Identify Risks | 1 | Risk Register
Project Procurement Management
| Plan Procurement Management |  |  | Conduct Procurements |  |  | Control Procurements |  |  | Close Procurements
| Plan Procurement Management | Inputs |  | Conduct Procurements | Inputs |  | Control Procurements | Inputs |  | Close Procurements | Inputs
| Plan Procurement Management | 1 | PMP | Conduct Procurements | 1 | Procurement MP | Control Procurements | 1 | PMP | Close Procurements | 1 | PMP
| Plan Procurement Management | 2 | Requirements Documentation | Conduct Procurements | 2 | Procurement SOW | Control Procurements | 2 | WPD | Close Procurements | 2 | Procurement Documents
| Plan Procurement Management | 3 | Activity Resource Requirements | Conduct Procurements | 3 | Procurement Documents | Control Procurements | 3 | WPR | Close Procurements | T&T
| Plan Procurement Management | 4 | Project Schedule | Conduct Procurements | 4 | Source Selection Criteria | Control Procurements | 4 | Approved Change Requests | Close Procurements | 1 | Procurement Audits
| Plan Procurement Management | 5 | Activity Cost Estimates | Conduct Procurements | 5 | Make-or-Buy decisions | Control Procurements | 5 | Procurement Documents | Close Procurements | 2 | Procurement Negotiations
| Plan Procurement Management | 6 | Risk Register | Conduct Procurements | 6 | Seller Proposals | Control Procurements | 6 | Agreements | Close Procurements | 3 | Records Management System
| Plan Procurement Management | 7 | Stakeholder Register | Conduct Procurements | 7 | PD | Control Procurements | T&T |  | Close Procurements | Outputs
| Plan Procurement Management | 8 | EEF | Conduct Procurements | 8 | OPA | Control Procurements | 1 | Contract Change Control System | Close Procurements | 1 | Closed Procurements
| Plan Procurement Management | 9 | OPA | Conduct Procurements | T&T |  | Control Procurements | 2 | Procurement Performance Reviews | Close Procurements | 2 | OPA Updates
| Plan Procurement Management | T&T |  | Conduct Procurements | 1 | EJ | Control Procurements | 3 | Inspection & Audits
| Plan Procurement Management | 1 | EJ | Conduct Procurements | 2 | Analytical Techniques | Control Procurements | 4 | Performance Reporting
| Plan Procurement Management | 2 | Meetings | Conduct Procurements | 3 | Bidder Conference | Control Procurements | 5 | Payment Systems
| Plan Procurement Management | 3 | Make-or-Buy Analysis | Conduct Procurements | 4 | Proposal Evaluation Techniques | Control Procurements | 6 | Claims Administration
| Plan Procurement Management | 4 | Market Research | Conduct Procurements | 5 | Independent Estimates | Control Procurements | 7 | Records Management System
| Plan Procurement Management | Outputs |  | Conduct Procurements | 6 | Advertising | Control Procurements | Outputs
| Plan Procurement Management | 1 | Procurement MP | Conduct Procurements | 7 | Procurement Negotiations | Control Procurements | 1 | WPI
| Plan Procurement Management | 2 | Procurement SOW | Conduct Procurements | Outputs |  | Control Procurements | 2 | Change Requests
| Plan Procurement Management | 3 | Procurement Documents | Conduct Procurements | 1 | Selected Sellers | Control Procurements | 3 | PMP Updates
| Plan Procurement Management | 4 | Source Selection Criteria | Conduct Procurements | 2 | Agreements | Control Procurements | 4 | PD Updates
| Plan Procurement Management | 5 | Make-or-Buy decisions | Conduct Procurements | 3 | Resource Calendars | Control Procurements | 5 | OPA Updates
| Plan Procurement Management | 6 | Change Requests | Conduct Procurements | 4 | Change Requests
| Plan Procurement Management | 7 | PD Updates | Conduct Procurements | 5 | PMP Updates
|  |  |  | Conduct Procurements | 6 | PD Updates
Project Stakeholder Management
| Identify Stakeholders |  |  | Plan Stakeholder Management |  |  | Manage Stakeholder Engagement |  |  | Control Stakeholder Engagement
| Identify Stakeholders | Inputs |  | Plan Stakeholder Management | Inputs |  | Manage Stakeholder Engagement | Inputs |  | Control Stakeholder Engagement | Inputs
| Identify Stakeholders | 1 | Project Charter | Plan Stakeholder Management | 1 | PMP | Manage Stakeholder Engagement | 1 | Change Log | Control Stakeholder Engagement | 1 | PMP
| Identify Stakeholders | 2 | Procurement Documents | Plan Stakeholder Management | 2 | Stakeholder Register | Manage Stakeholder Engagement | 2 | Communications MP | Control Stakeholder Engagement | 2 | WPD
| Identify Stakeholders | 3 | EEF | Plan Stakeholder Management | 3 | EEF | Manage Stakeholder Engagement | 3 | Stakeholder MP | Control Stakeholder Engagement | 3 | Issue Log
| Identify Stakeholders | 4 | OPA | Plan Stakeholder Management | 4 | OPA | Manage Stakeholder Engagement | 4 | OPA | Control Stakeholder Engagement | 4 | PD
| Identify Stakeholders | T&T |  | Plan Stakeholder Management | T&T |  | Manage Stakeholder Engagement | T&T |  | Control Stakeholder Engagement | T&T
| Identify Stakeholders | 1 | EJ | Plan Stakeholder Management | 1 | EJ | Manage Stakeholder Engagement | 1 | Interpersonal skills | Control Stakeholder Engagement | 1 | EJ
| Identify Stakeholders | 2 | Meetings | Plan Stakeholder Management | 2 | Meetings | Manage Stakeholder Engagement | 2 | Communication Methods | Control Stakeholder Engagement | 2 | Meetings
| Identify Stakeholders | 3 | Stakeholder Analysis | Plan Stakeholder Management | 3 | Analytical Techniques | Manage Stakeholder Engagement | 3 | Management Skills | Control Stakeholder Engagement | 3 | Information Management Systems
| Identify Stakeholders | Outputs |  | Plan Stakeholder Management | Outputs |  | Manage Stakeholder Engagement | Outputs |  | Control Stakeholder Engagement | Outputs
| Identify Stakeholders | 1 | Stakeholder Register | Plan Stakeholder Management | 1 | Stakeholder MP | Manage Stakeholder Engagement | 1 | Issue Log | Control Stakeholder Engagement | 1 | WPI
|  |  |  | Plan Stakeholder Management | 2 | PD Updates | Manage Stakeholder Engagement | 2 | Change Requests | Control Stakeholder Engagement | 2 | Change Requests
[7 empty] | Manage Stakeholder Engagement | 3 | PMP Updates | Control Stakeholder Engagement | 3 | PMP updates
[7 empty] | Manage Stakeholder Engagement | 4 | PD Updates | Control Stakeholder Engagement | 4 | PD Updates
[7 empty] | Manage Stakeholder Engagement | 5 | OPA Updates | Control Stakeholder Engagement | 5 | OPA updates
Note on D16: Project Charter: 1. Project purpose or justification 2. Measurable project objectives and related success criteria 3. High Level requirements 4. High Level Project description 5. High Level risks 6. Summary Milestone Schedule 7. Summary budget 8. Stakeholder List 9. Project Approval requirements 10. Assigned PM, responsibility and authority level 11. Name and authority of sponsor(s)
Note on F21: 1. Organisational culture, structure and governance 2. Geographic distribution of facilities and resources 3. Govt or Industry Standards 4. Infrastructure 5. Existing Human Resources 6. Personnel Administration 7. Company Work Authorization Systems 8. Marketplace conditions 9. Stakeholder Risk Tolerances 10. Political Climate 11. Organisations established Communication channels 12. Commercial Databases a. Standardized cost estimating data b. Industry Risk Study Information c. Risk Databases 13. PMIS
Note on F22: 1. Processes & Procedures 2. Corporate Knowledge Base a. Configuration Management Knowledge Base b. Financial Databases c. Historical Information & Lessons learnt d. Issue and Defect Management Database e. Process Measurement Database f. Project files from previous projects
Note on F25: Techniques: 1. Brainstorming 2. Conflict Resolution 3. Problem Solving 4. Meeting Management
Note on F27: Input: 1. Develop Project Management Plan 2. Plan Scope Management 3. Collect Requirements 4. Define Scope 5. Plan Schedule Management 6. Plan Cost Management 7. Plan Risk Management 8. Identify Stakeholders
Note on F145: 1. Cause & Effect 2. Flowcharts 3. Checksheets 4. Pareto Diagrams 5. Histograms 6. Control Charts 7. Scatter Diagrams
Note on F147: A statistical method
Note on F149: 1. Brainstorming 2. Force Field Analysis 3. Nominal Group Techniques 4. Quality Management & Control Tools
Note on F152: Input: Perform Quality Assurance
Note on F154: Input: Control Quality
Note on F172: 1. Heirarchical Type 2. Matrix based (RAM) eg RACI 3. Text oriented formats: Position Descriptions/Roles-Responsibilities-Authority formats
Note on F176: 1. Roles & responsibilities a. Role b. Authority c. Responsibility d. Competency 2. Project Organisation Charts 3. Staffing Management Plan a. Staff acquisition b. Resource Calendars eg Resource Histogram c. Staff release plan d. Training Needs e. Recognition and rewards f. Compliance g. Safety
Note on F197: Factors affecting choice of Comm Tech: 1. Urgency of the need for information 2. Availability of Technology 3. Ease of use 4. Project Environment 5. Sensitivity and Confidentiality of Information
Note on F198: Sequence of steps in basic comm model: 1. Encode 2. Transmit message 3. Decode 4. Acknowledge 5. Feedback/Response
Note on F199: 1. Interactive comm 2. Push comm 3. Pull comm
Note on F252: Type of contracts: 1. Fixed Price Contracts a. Firm Fixed Price (FFP) : Most common Type b. Fixed Price with Incentive Fee ( FPIF) c. Fixed Price with Economic Price Adjustment (FP-EPA): Protects both buyer and seller from external factors beyond their control 2. Cost Reimbursable Contracts a. Cost Plus Fixed Fee (CPFF) b. Cost Plus Incentive Fee (CPIF) c. Cost Plus Award Fee Contracts (CPAF) 3. Time & Materials (T&M)
Note on F261: Input: 1. Identify Risks 2. Conduct Procurements 3. Control Procurements 4. Close Procurements 5. Identify Stakeholders
Note on F262: Input: Conduct Procurements Some criteria: 1. Understanding of need 2. Overall or Life cycle cost 3. Technical Capability 4. Risk 5. Management Approach 6. Technical Approach 7. Warranty 8. Financial Capacity 9. Production capacity & Interest 10. Business Size and Type 11. Past performance of sellers 12. References 13. IPR 14. Propreitary rights
Note on F263: Input: Conduct Procurements
Note on F275: Output: Develop Project Charter
Note on F276: Output: Plan Procurement Management
Note on F282: Classification Models: 1. Power/Interest grid 2. Power/Influence grid 3. Influence/Impact grid 4. Salience Model a. Power b. Urgency c. Legitimacy
Note on I273: Levels of Stakeholder Engagement 1. Unaware 2. Resistant 3. Neutral 4. Supportive 5. Leading
Note on K18: Output: Develop Project Charter
Note on K24: Techniques: 1. Brainstorming 2. Conflict Resolution 3. Problem Solving 4. Meeting Management
Note on K42: Output: Plan Scope Management
Note on K43: Output: Identify Stakeholders
Note on K44: Output: Plan Stakeholder Management
Note on K48: Eg: JAD in Software QFD in Manufacturing
Note on K49: 1. Brainstorming 2. Nominal Group Technique 3. Idea/Mind Mapping 4. Affinity Diagram 5. Multi Criteria Decision analysis
Note on K50: Methods: 1. Unanimity eg Delphi Technique 2. Majority 3. Plurality 4. Dictatorship
Note on K52: Job Shadowing
Note on K53: eg Storyboarding
Note on K79: Input: Sequence Activities
Note on K125: Input: Determine Budget
Note on K136: Output: Plan Quality Management Contains: 1. Process Boundaries 2. Process configuration 3. Process metrics 4. Targets for improved performance
Note on K141: 1. Affinity Diagrams 2. Process Decision Program Charts 3. Interrelationship Digraphs 4. Tree Diagrams 5. Prioritization Matrices 6. Activity Network Diagrams ( AOA and AON) 7. Matrix Diagrams
Note on K173: 1. Availability 2. Cost 3. Experience 4. Ability 5. Knowledge 6. Skills 7. Attitude 8. International Factors
Note on K229: 1. Brainstorming 2. Delphi Technique 3. Interviewing 4. Root Cause Analysis
Note on K235: 1. Identified Risks 2. Potential responses
Note on K244: Output: Plan Procurement Management
Note on K245: Output: Plan Procurement Management
Note on K248: Output: Plan Procurement Management
Note on K276: Output: Identify Stakeholders
Note on K282: Stakeholder Engagement Assessment Matrix showing current engagement vs desired engagement
Note on P18: Output: Develop PMP
Note on P19: Output: Perform Integrated Change Control
Note on P24: A part of EEF: Sceduling Tools. Work Authorisation System, Configuration Management System, Information Collection and Distribution system, Interfaces to other online automated systems
Note on P25: Types: 1. Information Exchange 2. Brainstorming 3. Decision Making
Note on P27: Input: Control Quailty
Note on P28: Input: All Monitor & Control Process groups except in Project Integration Management
Note on P46: Eg: JAD in Software QFD in Manufacturing
Note on P47: Techniques: 1. Product Breakdown 2. Systems Analysis 3. Requirements Analysis 4. System Engineering 5. Value Engineering 6. Value Analysis
Note on P48: General Management Techniques such as: 1. Brainstorming 2. Lateral Thinking 3. Analysis of Alternatives
Note on P50: 1. Product Scope Description 2. Deliverable 3. Acceptance Criteria 4. Exclusions 5. Constraints 6. Assumptions
Note on P72: Output: Define Activities
Note on P76: Four types of dependencies/ relationships: 1. FS 2. SS 3. FF 4. SF
Note on P77: 1. Mandatory: Hard logic/Hard Dependencies 2. Discretionary : Preferred Logic/Preferential Logic/Soft Logic 3. External 4. Internal
Note on P80: Input: Develop Schedule
Note on P109: Output: Estimate Costs
Note on P122: Input: Control Costs
Note on P139: Output: Plan Quality Management eg: Function Points, Mean Time Between Failure (MTBF) and Mean Time to Repair (MTTR)
Note on P140: Output: Plan Quality Management
Note on P145: 1. Cause & Effect 2. Flowcharts 3. Checksheets 4. Pareto Diagrams 5. Histograms 6. Control Charts 7. Scatter Diagrams
Note on P149: Input: Perform Quality Assurance
Note on P150: Input: Monitor & Control Project Work
Note on P151: Input: Validate Scope
Note on P169: 1. Leadership 2. Team Building 3. Motivation 4. Communication 5. Influencing 6. Decision Making Styles: a. Command b. Consultation c. Consensus d. Coin Flip Factors: a. Time Constraints b. Trust c. Quality d. Acceptance Phase Model: a. Problem Definition b. Problem Solution Generation c. Ideas to action d. Solution Action Planning e. Solution Evaluation Planning f. Evaluation of the outcome and processes 7. Political and Cultural awareness 8. Negotiation 9. Trust Building 10. Conflict Management 11. Coaching
Note on P171: Tuckman Ladder: 1. Forming 2. Storming 3. Norming 4. Performing 5. Adjourning
Note on P193: Output: Manage Stakeholder Engagement
Note on P275: Output: Perform Integrated Changed Control
Note on P280: 1. Leadership 2. Team Building 3. Motivation 4. Communication 5. Influencing 6. Decision Making Styles: a. Command b. Consultation c. Consensus d. Coin Flip Factors: a. Time Constraints b. Trust c. Quality d. Acceptance Phase Model: a. Problem Definition b. Problem Solution Generation c. Ideas to action d. Solution Action Planning e. Solution Evaluation Planning f. Evaluation of the outcome and processes 7. Political and Cultural awareness 8. Negotiation 9. Trust Building 10. Conflict Management 11. Coaching
Note on P284: Input: 1. Manage Project Team 2. Control Communications 3. Control Stakeholder Engagement
Note on U18: Output: Develop PMP
Note on U19: Output: All control processes except in Project Integration management knowledge area
Note on U20: Output: Control Schedule
Note on U21: Output: Control Costs
Note on U22: Output: Control Quailty
Note on U27: A part of EEF: Sceduling Tools. Work Authorisation System, Configuration Management System, Information Collection and Distribution system, Interfaces to other online automated systems
Note on U28: Types: 1. Information Exchange 2. Brainstorming 3. Decision Making
Note on U29: Examples: 1. Regression Analysis a. Ordinary Least Squares(OLS) regression b. Logistic regression c. Heirarchical linear modelling d. Duration models 2. Grouping methods a. Discriminant Function analysis b. Cluster Analysis 3. Causal Analysis 4. Root Cause analysis 5. Forecasting method (Time series, Scenario Building. Simulation) 6. FMEA 7. Fault Tree Analysis (FTA) 8. Reserve Analysis 9. Trend Analysis 10. EVM 11. Variance Analysis
Note on U31: Input: 1. Perform Integrated Change Control 2. Manage Project Team 3. Manage Communications 4. Control Risks 5. Control Procurements
Note on U49: Includes: 1. PSS 2. WBS 3. WBS dictionary
Note on U110: 1. Variance Analysis a. SV = EV - PV b. CV = EV - AC c. VAC = BAC - EAC 2. Trend Analysis 3. Earned Value Performance
Note on U113: 3 key dimensions: 1. PV 2. EV 3. AC Variance monitored by 1. SV = EV - PV 2. CV = EV - AC 3. SPI = EV/PV 4. CPI = EV/AC
Note on U114: 1. EAC = AC = Bottom-up ETC 2. EAC = AC + (BAC-EV) 3. EAC = BAC/CPI 4. EAC = AC + [(BAC-EV)/(SPIxCPI)]
Note on U115: 1. TCPI = (BAC-EV)/(BAC-AC) 2. TCPI = (BAC-EV)/(EAC-AC)
Note on U168: Output: Develop Project Team
Note on U169: Output: Manage Stakeholder Engagement
Note on U172: 1. Leadership 2. Team Building 3. Motivation 4. Communication 5. Influencing 6. Decision Making Styles: a. Command b. Consultation c. Consensus d. Coin Flip Factors: a. Time Constraints b. Trust c. Quality d. Acceptance Phase Model: a. Problem Definition b. Problem Solution Generation c. Ideas to action d. Solution Action Planning e. Solution Evaluation Planning f. Evaluation of the outcome and processes 7. Political and Cultural awareness 8. Negotiation 9. Trust Building 10. Conflict Management 11. Coaching
Note on U175: 1. Withdraw/Avoid 2. Smooth/Accommodate 3. Compromise/Reconcile 4. Force/Direct 5. Collaborate/Problem Solve
Note on U221: 1. Interviewing 2. Probability distributions a. Continuous b. Discrete c. Uniform
Note on Z18: Output: Develop PMP
Note on Z19: Output: Monitor & Control Project Work
Note on Z20: Output: 1. Executing Process group 2. Monitor & control Process group 3.Plan Procurement Management
Note on Z25: Types: 1. Information Exchange 2. Brainstorming 3. Decision Making
Note on Z26: May be manual or automated
Note on Z28: Inputs: 1. Direct & Manage Project Work 2. Control Quality 3. Control Procurements
Note on Z29: Input: Manage Stakeholder Engagement
Note on Z44: Output: Control Quality
Note on Z49: Input: Close Project or Phase
Note on Z82: 1. Triangular Distribution = (tP + tM + tO)/3 2. PERT / Beta Distribution = (tP + 4tM + tO)/6
Note on Z217: 1. Avoid 2. Transfer 3. Mitigate 4. Accept
Note on Z218: 1. Exploit 2. Enhance 3. Share 4. Accept
Note on AE18: Output: Develop PMP
Note on AE19: Output: Validate Scope
Note on AE23: Types: 1. Information Exchange 2. Brainstorming 3. Decision Making
Note on AE24: Examples: 1. Regression Analysis a. Ordinary Least Squares(OLS) regression b. Logistic regression c. Heirarchical linear modelling d. Duration models 2. Grouping methods a. Discriminant Function analysis b. Cluster Analysis 3. Causal Analysis 4. Root Cause analysis 5. Forecasting method (Time series, Scenario Building. Simulation) 6. FMEA 7. Fault Tree Analysis (FTA) 8. Reserve Analysis 9. Trend Analysis 10. EVM 11. Variance Analysis
Note on AE72: Output: Sequence Activities
Note on AE85: 1. Resource Leveling : Crit Path Changes often increases 2. Resource Smoothing : Crit Path remains same
Note on AE86: 1. What-If Scenario 2. Simulation
Note on AE88: 1. Crashing : Increasing resources 2. Fast-Tracking : Parallel activities
Note on AE92: Format: 1. Bar Chart 2. Milestone chart 3. Project Schedule Network Diagram
Note on AJ75: 1. Trend Analysis 2. CPM 3. CCM 4. EVM
Note on AJ77: 1. Resource Leveling : Crit Path Changes often increases 2. Resource Smoothing : Crit Path remains same
Note on AJ78: 1. What-If Scenario 2. Simulation
Note on AJ80: 1. Crashing : Increasing resources 2. Fast-Tracking : Parallel activities

## Acronyms
Acronyms
EEF | Enterprise Environmental factors
OPA | Organisational Process Assets
PMP | Project Management Plan
EJ | Expert Judgment
WPD | Work Performance Data
WPI | Work Performance Information
WPR | Work Performance Reports
PD | Project Documents
MP | Management Plan
GCT | Group Creativity Technique
GDMT | Group Decision Making Technique
RTM | Requirements Traceability matrix
PSS | Project Scope Statement
PDM | Precedence Diagramming method
L&L | Leads and Lags
PSDN | Project Schedule Network Diagram
WBS | Work Breakdown Structure
RBS | Resource Breakdown Structure
PMS | Project Management Software
PFR | Project Funding requirements
HR | Human Resource
SOW | Statement of Work
EVM | Earned value Management
EMV | Expected Monetary value

## Some Rules for ITTO
Some rules for ITTO
Only Planning group to have Change Requests output is Plan Procurement Management
PMIS | T&T used in Direct & Manage Project Work and Monitor & Control Project Work
EEF | Input: 1st 5 processes of Project Integration Management
OPA | Input: All 6 processes of Project Integration Management
EJ | T&T : All 6 processes of Project Integration Management
EJ, Meetings , Analytical Techniques: | T&T for Monitor & Control Project Work ( + PMIS), Close Project or Phase, Plan Schedule Management, Plan Cost management, Plan Risk Management, Plan Stakeholder Management
Information Management Systems | T&T for Manage Communications , Control Communication and Control Stakeholder Engagement
WPI, Change req, PMP Update, PD Update, OPA update | Output for all control Processes: Control Scope, Control Schedule ( + Schedule Forecast), Control Cost ( + Cost Forecast), Control Quality ( +Quality Control Measurements, Validated Changes, Verified Deliverables), Control Communication, Control Risk, Control Procurement, Control Stakeholder ENgagement
WPD | Input to all M&C processes except in Project Integration Management
PMS | T&T for Estimate Activity Duration, Control Schedule, Estimate Costs, Control Costs
Project Charter, PMP, EEF, OPA | Input to Plan Integration Mgmnt, Plan Scope Mgmnt,Plan Schedule Mgmnt, Plan Cost Mgmnt, Plan Risk Mgmnt ( + Stakeholder Register)
--Project Charter | In addition to above Collect requirements, Define Scope and Identify Stakeholders
Neither EEF, OPA | Collect Requirements, Validate Scope, Perform Quality Assurance, Develop Project team, Plan Risk Response, Control Risks,Control Procurements, Close Procurements, Control Stakeholder Engagement
EEF Updates | Only through Develop Project Teams and Manage Project Teams
Performance Reporting | Manage Communications and Control Procurements
Issue log | Input to Manage Project Team, Control Communications, Control Stakeholder Engagement
Agreements | Input to Develop Project Charter and Control Procurements
GDMT | Collect Requirements, Validate Scope, Estimate Activity Durations, Estimate Costs
Reserve analysis | Estimate Activity Durations, Estimate Costs, Determine Budget, Control Costs, Control risks
Performance reviews | Control Schedule, Control Costs, Control Procurements
Inspection | Validate Scope ,Control quality
Audits | Control Quality, Control Risks, Close Procurements
Inspection & audits | Conduct Procurements
Interpersonal skills | Develop Project team, manage Project team, Manage Stakeholder engagement
Resource calendars | Output Acquire Project Team & Conduct Procurements
WPR | Input to Perform Integrated change control, manage project team, manage communication. Control risk, control procurement
Risk register | Input to Estimate Activity Resources, Estimate Activity Durations, Develop Schedule, Estimate costs, Determine Budget, Plan QM, Perform Qualitative Risk Analy, Perform Quantitative risk analy, Plan Risk Repsonses, Control Risks, Plan Procurement Mgmnt
Only OPA | Close Project or Phase, Define Scope, Control Scope, Control Schedule, Control Costs, Control Quality, Manage Project Team, Control Communications, Conduct procurement, Manage Stakeholder Engagement
Procurement Documents | Input to Identify risks, Conduct procurements, Control procurements, close procurements, identify stakeholders
Approved Change Requests | Input to Direct & manage Project Work, Control Quality, Control Procurements
Project Docs | Input to Control Qlty, Identify Risks, Conduct Procurements, Control Stakeholder Engagements
Activity Resource Requirements | Input to Estimate Activity Duration, Develop Schedule, Plan HR Management, Plan Procurement Management
Activity Duration Estimates | DeveloP Schedule, Identify Risks
Stakeholder MP | Input to Collect Requirements and manage stakeholder engagement