## Sheet1
| Initiating | Planning | Executing | Monitoring & Controlling | Closing
Project Integration Management | Develop Project Charter | Develop Project Management Plan | Direct and Manage Project Work | Monitor and Control Project Work | Close Project or Phase
| Project Statement of Work | Project Charter | Project Management Plan | Project Management Plan | Project Management Plan
| Business Case | Outputs from other processes | Approved Change Requests | Schedule Forecasts/Cost Forecasts | Accepted Deliverables
| EEF & OPA | EEF & OPA | EEF & OPA | EEF & OPA | OPA
| Contracts/Agreements |  |  | Work Performance Information
Validated Changes
| Expert Judgement | Expert Judgement | Expert Judgement | Expert Judgement | Expert Judgement
| Facilitation Techniques | Facilitation Techniques | PMIS | PMIS
|  |  |  | Analytical Techniques | Analytical Techniques
|  |  |  | Meetings | Meetings
|  |  | Deliverables |  | Final product, service or result transition
| Project Charter | PMP | Work Performance Data | Work Performance Reports | OPA updates
|  |  | Change Requests | Change Requests
|  |  | PMP Updates | PMP Updates
|  |  | Project Document Updates | Project Document Updates
Perform Integrated Change Control
Project Management Plan
Work Performance Reports
Change Requests
EEF & OPA
Expert Judgement
Meetings
Change Control Tools
Approved Change Requests
Change Log
PMP Updates
Project Document Updates
Project Scope Management |  | Plan Scope Management
PMP
Project Charter
EEF & OPA
Exopert Judgement
Meetings
Scope Management Plan
Requirements Management Plan
|  | Collect Requirements |  | Validate Scope
|  | Scope Management Plan |  | Project Management Plan
|  | Requirements Management Plan |  | Requirements Documentation
|  | Stakeholder Management Plan |  | Requirements Traceability Matrix
|  | Project Charter |  | Verified Deliverables
|  | Stakeholder Register |  | Work Performance Data
|  | Interviews |  | Inspection
|  | Group Decision-Making Techniques |  | Group Decision-Making Techniques
|  | Facilitated workshops |  | Accepted Deliverables
|  | Group Creativity techniques |  | Change Requests
|  | Focus Groups |  | Work Perfomance Information
|  | Questionnaires and Surveys |  | Project Document Updates
Observations
Prototypes
Benchmarking
Document Analysis
Context Diagrams
Requirements Documentation
Requirements Traceability Matrix
|  | Define Scope |  | Control Scope
|  | Scope Management Plan |  | Project Management Plan
|  | Project Charter |  | Requirements Documentation
|  | Requirements Documentation |  | Requirements Traceability Matrix
|  | OPA |  | Work Performance Data
|  | Expert Judgement |  | OPA
|  | Product Analysis |  | Variance Analysis
|  | Alternatives Generation |  | Work Performance Information
|  | Facilitated Workshops |  | OPA updates
|  | Project Scope Statement |  | Change Requests
PMP Updates
|  | Project Document Updates |  | Project Document Updates
Create WBS
Scope Management Plan
Project Scope Statement
Requirements Documentation
EEF & OPA
Decomposition
Expert Judgement
Scope Baseline
Project Document updates
Project Time Management |  | Plan Schedule Management
PMP
Project Charter
EEF & OPA
Expert Judgement
Analytical Techniques
Meetings
Schedule Management Plan
Define Activities
Schedule Management Plan
Scope Baseline
EEF & OPA
Decomposition
Rolling Wave Planning
Expert Judgement
Activity List
Activity attributes
Milestone List
Sequence Activities
Schedule Management Plan
Activity List
Activity Attributes
Milestone List
Project Scope Statement
EEF & OPA
Precedence Diagramming (PDM)
Dependency Determination
Applying Leads and Lags
Project Schedule Network Diagrams
Project Document Updates
Estimate Activity Resources
Schedule Management Plan
Activity List
Activity Attributes
Resource Calendars
Risk Register
Activity Cost Estimates
EEF & OPA
Expert Judgement
Alternative Analysis
Published Estimating Data
Bottom-up Estimating
Project Management Software
Activity Resource Requirements
Resource Breakdown Structure
Project Document Updates
Estimate Activity Durations
Schedule Management Plan
Activity List
Activity Attributes
Activity Resource Requirements
Resource Calendars
Resource Breakdown Structure
Risk Register
Project Scope Statement
EEF & OPA
Expert Judgement
Analogous estimating
Parametric estimating
Three-point estimates (PERT)
Group-Decision Making Techniques
Reserve Analysis
Activity Duration Estimates
Project Document Updates
|  | Develop Schedule |  | Control Schedule
|  | Schedule Management Plan |  | PMP
|  | Activity List |  | Project Schedule
|  | Activity Attributes |  | Work Performance Data
|  | Project Schedule Network Diagrams |  | Project Calendars
|  | Activity Resource Requirements |  | Schedule Data
|  | Resource Calendars |  | OPA
|  | Activity Duration Estimates |  | Performance reviews
|  | Project Scope Statement |  | Variance analysis
|  | Risk Register |  | Project Management Software
|  | Project Staff Assignments |  | Resource Levelling
|  | Resource Breakdown Structure |  | What-if scenario
|  | EEF & OPA |  | Adjusting leads and lags
|  | Schedule network analysis |  | Schedule compression
|  | Critical Path Method |  | Scheduling tool
|  | Critical Chain Method |  | Work Performance measurements
|  | Resource Optimization Techniques |  | OPA updates
|  | Modeling Techniques |  | Change Requests
|  | Leads and Lags |  | Project Management Plan updates
|  | Schedule Compression |  | Project document updates
Scheduling Tool
Schedule Baseline
Project Schedule
Schedule Data
Project Calendars
PMP Updates
Project Document Updates
Project Cost Management |  | Plan Cost Management |  | Control Costs
|  | Project Management Plan |  | Project Management Plan
|  | Project Charter |  | Project funding requirements
|  | EEF & OPA |  | Work performance information
|  | Expert Judgement |  | OPA
|  | Analytical Techniques |  | Earned Value Management (EVM)
|  | Meetings |  | Forecasting
|  | Cost Management Plan |  | To-complete performance index
|  | Estimate Costs |  | Performance reviews
|  | Cost Management Plan |  | Variance analysis
|  | Human Resource Management Plan |  | Project Management software
Scope Baseline
Project Schedule
Risk Register
|  | EEF & OPA |  | Work performance measurements
|  | Expert Judgement |  | Budget forecasts
|  | Analogous stimating |  | OPA updates
|  | Parametric Estimating |  | Change requests
|  | Bottom-up Estimating |  | Project management plan updates
|  | Three-point Estimates |  | Project document updates
Reserve Analysis
Cost of Quality
Project Management Software
Vendor Bid Analysis
Group Decision-Making Techniques
Activity Cost Estimates
Basis of Estimates
Project Documents Updates
Determine Budget
Cost Management Plan
Activity Cost Estimates
Basis of Estimates
Scope Baseline
Project Schedule
Resource Calendars
Risk Register
Agreements/Contracts
OPA
Cost Aggregation
Reserve Analysis
Expert Judgement
Historical Relationships
Funding Limit Reconciliation
Cost Baseline
Project Funding Requirements
Project Document Updates
Project Quality Management |  | Plan Quality Management | Perform Quality Assurance | Control Quality
|  | Project Management Plan | Quality Management Plan | Project Management Plan
|  | Stakeholder Register | Process Improvement Plan | Quality Metrics
|  | Risk Register | Quality Metrics | Quality Checklists
|  | Requirements Documentation | Quality Cotrol Measurements | Work Performance Data
|  | EEF & OPA | Project Documents | Approved Change Requests
|  | Cost-benefit analysis | Quality Mgmt&Control Tools | Deliverables
|  | Cost of Quality | Quality Audits | Project Documents
|  | Seven Basic Quality Tools | Proces Analysis | OPA
|  | Benchmarking | OPA updates | Seven Basic Quality Tools
|  | Design of Experiments | Change Requests | Statistical Sampling
|  | Statistical Sampling | PMP Updates | Inspection
|  | Additional Quality Planning Tools | Project Document Updates | Approved Change Requests Review
|  | Meetings |  | Quality Control Measurements
|  | Quality Management Plan |  | Validated Changes
|  | Process Improvement Plan |  | Verified Deliverables
|  | Quality Metrics |  | Work Performance Information
|  | Quality Checklists |  | Change Requests
Project Management Plan Updates
OPA Updates
|  | Project Document Updates |  | Project Document Updates
Project Human Resources Management |  | Plan Human Resource Management | Acquire Project Team
|  | Project Management Plan | Human Resource Management Plan
Activity Resource Requirements
|  | EEF & OPA | EEF & OPA
|  | Organization Charts&Position Descr. | Pre-Assignment
|  | Networking | Negotiation
|  | Organizational Theory | Acquisition
|  | Expert Judgement | Virtual Teams
|  | Meetings | Multi-Criteria Decision Analysis
|  | Human Resource plan | Project Staff Assignments
Resource Calendars
Project Management Plan Updates
Develop Project Team
Human Resource Management Plan
Resource Staff Assignments
Resource Calendars
Interpersonal skills
Training
Team-Building Activities
Ground Rules
Co-location
Recognition and Rewards
Personnel Assesment Tools
Team Performance Assessments
EEF Updates
Manage Project Team
Human Resource Management Plan
Project Staff Assignments
Team Performance Assessments
Issue Log
Work Performance Reports
OPA
Observation and Conversation
Project Performance Appraisals
Conflict Management
Interpersonal skills
OPA & EEF Updates
Change Requests
Project Document Updates
Project Management Plan Updates
Project Communications Management |  | Plan Communications | Manage Communications | Control Communications
|  | Project Management Plan | Communications Management Plan | Project Management Plan
|  | Stakeholder Register | Work Performance Reports | Project Communications
|  | EEF & OPA | EEF & OPA | Issue Log
Work Performance Data
OPA
|  | Communication Requirements Analysis | Information Management Systems | Information Management System
|  | Communication Technology | Communication Technology | Expert Judgement
|  | Communication Models | Communication Models
|  | Communication Methods | Communication methods | Reporting systems
|  | Meetings | Performance Reporting | Meetings
|  | Communications Management Plan | Project Communications | Work Performance Information
|  |  | Project Management Plan Updates | Project Management Plan Updates
|  | Project Document Updates | Project Documents Updates | Project Document Updates
|  |  | OPA Updates | OPA Updates
Change Requests
Project Risk Management |  | Plan Risk Management |  | Control Risks
|  | Project Management Plan |  | Project Management Plan
|  | Project Charter |  | Risk Register
|  | Stakeholder Register |  | Work Perfomance Data
|  | EEF & OPA |  | Work Performance Reports
|  | Analytical Techniques |  | Risk Reassessment
|  | Expert Judgment |  | Risk Audits
|  | Meetings |  | Variance and Trend Analysis
Technical Performance Measurement
Reserve Analysis
Meetings
|  | Risk Management Plan |  | Work Performance Information
Change Requests
PMP Updates
Project Documents Updates
OPA Updates
Identify Risks
Risk Management Plan
Cost Management Plan
Schedule Management Plan
Quality Management Plan
Human Resource Management Plan
Scope Baseline
Activity Cost Estimates
Activity Duration Estimates
Stakeholder Register
Project Documents
Procurement Documents
EEF & OPA
Documentation Reviews
Information Gathering Techniques
Checklist Analysis
Assumptions Analysis
Diagramming Techniques
SWOT Analysis
Expert Judgement
Risk Register
Perform Qualitative Risk Analysis
Risk Management Plan
Scope Baseline
Risk Register
EEF & OPA
Risk Probability and Impact Assessments
Probability and Impact Matrix
Risk Data Quality Assessments
Risk Categorization
Risk Urgency Assessment
Expert Judgement
Risk Register Updates
Perform Quantitative Risk Analysis
Risk Management Plan
Cost Management Plan
Schedule Management Plan
Risk Register
EEF & OPA
Data Gathering and Representation Techniques
Quantitative Risk Analysis and Modeling Techniques
Expert Judgement
Project Document Updates
Plan Risk Responses
Risk Management Plan
Risk Register
Strategies for Negative Risks or Threats
Strategies for Positive Risks or Opportunities
Contingent Response Strategies
Expert Judgement
PMP Updates
Project Document Updates
Project Procurement Management |  | Plan Procurement Management | Conduct Procurements | Control Procurements | Close Procurement
|  | Project Management Plan | Project Management Plan | Project Management Plan | Project Management plan
|  | Requirements Documentation | Procurement Documents | Procurement Documents | Procurement documentation
|  | Risk Register | Source Selection Criteria | Agreements
|  | Activity Resource Requirements | Seller Proposals | Approved Change Requests
|  | Project Schedule | Project Documents | Work Performance Reports
|  | Activity Cost Estimates | Make-or-Buy Decisions | Work Performance Data
|  | Stakeholder Register | Project Statement of Work
|  | EEF & OPA | OPA
|  | Make-or-Buy Analysis | Bidder Conferences | Contract Change Control System | Procurement Audits
|  | Expert Judgement | Proposal Evaluation Techniques | Procurement Performance Reviews | Procurement Negotiations
|  | Market Research | Independent Estimates | Inspection and Audits | Records Management System
|  | Meetings | Expert Judgement | Performance Reporting
|  |  | Advertising | Payment Systems
|  |  | Analytical Techniques | Claims Administration
|  |  | Procurement Negotiations | Records Management System
Procurement Management Plan
|  | Procurement Statement of Work | Selected Sellers | Work Performance Information | Close Procurements
|  | Procurement Documents | Agreements | OPA Updates | OPA Updates
|  | Source Selection Criteria | Resource Calendars
|  | Make-or-Buy Decisions | Change Requests | Change Requests
|  | Change Requests | Project Management Plan Updates | Project Management Plan Updates
|  | Project Documents Updates | Project Documents Updates | Project Documents Updates
Project Stakeholder Management | Identify Stakeholders | Plan Stakeholder Management | Manage Stakeholder Engagement | Control Stakeholder Engagement
| Project Charter | Project Manangement Plan | Stakeholder Management Plan | Project Management Plan
| Procurement Documents | Stakeholder Register | Communications Management Plan | Issue Log
| EEF & OPA | EEF & OPA | Change Log | Work Performance Data
|  |  | OPA | Project Documents
| Stakeholder Analysis | Communication methods | Communication Methods | Information Management Systems
| Expert Judgement | Expert Judgement | Interpersonal Skills | Expert Judgment
| Meetings | Analytical Techniques | Management Skills | Meetings
| Stakeholder Register | Stakeholder Management Plan | OPA updates | Work Performance Information
|  | Project Document Updates | Change requests | Change Requests
|  |  | Project Management plan updates | Project Management Plan Updates
|  |  | Project document updates | Project Document Updates
OPA